NEITI DIAGNOSTIC REVIEW FRAMEWORK

Memo to the NSWG Board Meeting of 18 July 2024

A Comprehensive Implementation Framework for Diagnostic Studies, Assessments, and Analyses

Document Reference: NEITI/NSWG/DRF/2024/002

FOREWORD

The Nigeria Extractive Industries Transparency Initiative (NEITI) is committed to the highest standards of transparency, accountability, and good governance in the management of Nigeria's oil, gas, and solid minerals resources. As an implementing country of the Extractive Industries Transparency Initiative (EITI), NEITI is required to subject its performance to rigorous Validation assessments against the EITI Standard.

The 2023 Validation exercise identified a range of corrective actions, recommendations, and governance issues requiring systematic diagnostic reviews, assessments, and analyses. These diagnostic exercises are essential to strengthening NEITI's institutional effectiveness, enhancing stakeholder engagement, and addressing specific transparency and accountability gaps identified in Nigeria's extractive sector governance.

This Diagnostic Review Framework has been developed to provide a structured, systematic, and prioritised approach to undertaking the diagnostic studies, assessments, and analyses required to address Validation findings and strengthen NEITI's implementation of the EITI Standard. The framework ensures that each diagnostic review is conducted with clear objectives, defined scope, appropriate methodology, and measurable outcomes, while recognising the resource constraints facing the Initiative.

The NSWG  is invited to deliberate, consider and approve the proposed diagnostic reviews contained in this framework. Implementation will be staggered based on the availability of financial resources and is expected to commence from the 2024 financial year onwards. The framework provides a mechanism for scheduling diagnostic studies over the life of NEITI's rolling Five-Year Strategic Plan (2022 - 2026), with provision for additional studies to be incorporated as needs arise.

TABLE OF CONTENTS

| Section | Title |
| --- | --- |
| 1.0 | Introduction and Background |
| 2.0 | Purpose and Scope of the Framework |
| 3.0 | Guiding Principles |
| 4.0 | Diagnostic Review Categories |
| 5.0 | Detailed Diagnostic Review Schedule |
| 6.0 | Implementation Approach |
| 7.0 | Resource and Funding Considerations |
| 8.0 | Linkages to NEITI's Five-Year Strategic Plan |
| 9.0 | Monitoring, Evaluation, and Reporting |
| 10.0 | Framework Flexibility and Amendments |
| 11.0 | NSWG Review, Deliberation, and Approval |
| 12.0 | Annexes |

LIST OF ACRONYMS

| Acronym | Full Meaning |
| --- | --- |
| APR | Annual Progress Report |
| AFS | Audited Financial Statements |
| AuGF | Auditor-General of the Federation |
| BO | Beneficial Ownership |
| BOD | Beneficial Ownership Disclosure |
| CAC | Corporate Affairs Commission |
| CSO | Civil Society Organisation |
| CSSC | Civil Society Steering Committee |
| DSDP | Direct Sale Direct Purchase |
| EITI | Extractive Industries Transparency Initiative |
| FASD | Fiscal Allocation and Statutory Disbursement |
| FG | Federal Government |
| GCEO | Group Chief Executive Officer |
| HMSMD | Honourable Minister of Solid Minerals Development |
| IA | Independent Administrator |
| IATT | Inter-Agency Task Team |
| IMTT | Inter-Ministerial Task Team |
| IOC | International Oil Company |
| MCO | Mining Cadastre Office |
| MSG | Multi-Stakeholder Group |
| NASS | National Assembly |
| NCDMB | Nigerian Content Development and Monitoring Board |
| NDDC | Niger Delta Development Corporation |
| NEITI | Nigeria Extractive Industries Transparency Initiative |
| NFIU | Nigerian Financial Intelligence Unit |
| NMDPRA | Nigerian Midstream and Downstream Petroleum Regulatory Authority |
| NNPC | Nigerian National Petroleum Corporation |
| NNPCL | Nigerian National Petroleum Company Limited |
| NSWG | National Stakeholders' Working Group |
| NUPRC | Nigerian Upstream Petroleum Regulatory Commission |
| OAGF | Office of the Accountant-General of the Federation |
| OAuGF | Office of the Auditor-General of the Federation |
| OML | Oil Mining Lease |
| OPAs | Oil Processing Agreements |
| OSGF | Office of the Secretary to the Government of the Federation |
| PIA | Petroleum Industry Act |
| RMFAC | Revenue Mobilisation Allocation and Fiscal Commission |
| RPL | Resource-Backed Loan |
| SAT | Self-Assessment Tool |
| SGF | Secretary to the Government of the Federation |
| SOE | State-Owned Enterprise |
| ToR | Terms of Reference |
| TUGAR | Transparency, Accountability, and Good Governance in Resource-rich Economies |

- INTRODUCTION AND BACKGROUND

1.1 NEITI's Mandate and EITI Obligations

The Nigeria Extractive Industries Transparency Initiative (NEITI) was established by the NEITI Act No. 31 of 2007 to ensure due process and transparency in the payments made by all extractive industry companies to the Federal Government and statutory recipients. As an implementing country of the EITI, NEITI is required to adhere to the EITI Standard, which sets out the requirements for transparency and accountability in the governance of oil, gas, and mineral resources.

1.2 The Validation Process

Validation is the EITI's quality assurance mechanism, providing a rigorous, independent assessment of how well a country is implementing the EITI Standard. Following Nigeria's Validation exercise, a comprehensive set of findings, corrective actions, and recommendations were identified across multiple requirements of the EITI Standard. These findings necessitate systematic diagnostic reviews, assessments, and analyses to address identified weaknesses and strengthen implementation.

1.3 Rationale for a Diagnostic Review Framework

The NSWG recognises that addressing the Validation findings requires a structured, prioritised, and resourced approach to we s. A diagnostic review framework provides:

- Systematic Coverage: Ensuring all identified issues are addressed in a coordinated manner.

- Prioritisation: Allocating resources to the most critical and impactful reviews first.

- Accountability: Establishing clear responsibilities, timelines, and deliverables.

- Flexibility: Allowing for the incorporation of additional diagnostic needs as they arise.

- Strategic Alignment: Linking diagnostic reviews to NEITI's broader strategic objectives.

1.4 Basis of the Framework

This framework is based on:

- The EITI Validation Report on Nigeria's implementation of the EITI Standard.

- The Remedial Action Plan developed by NEITI to address Validation findings.

- The self-assessment questions and requirements identified across the transparency templates.

- The specific commitments made by Nigeria during the Validation assessment.

- NEITI's Five-Year Strategic Plan (2022–2026).

2.0 PURPOSE AND SCOPE OF THE FRAMEWORK

2.1 Purpose

The purpose of this Diagnostic Review Framework is to:

- Provide a structured and systematic approach for the NSWG to commission, oversee, and utilise diagnostic reviews, assessments, and analyses.

- Address the corrective actions, recommendations, and governance issues identified in the Validation process.

- Strengthen NEITI's implementation of the EITI Standard across all relevant requirements.

- Enhance the transparency, accountability, and effectiveness of Nigeria's extractive sector governance.

- Support evidence-based policy making and reforms in the oil, gas, and solid minerals sectors.

- Ensure that diagnostic reviews are conducted with clear objectives, defined scope, appropriate methodology, and measurable outcomes.

- Provide a mechanism for scheduling diagnostic studies over the life of NEITI's rolling Five-Year Strategic Plan.

2.2 Scope

This framework covers diagnostic reviews, assessments, and analyses required to address:

- MSG Governance Issues: Including NSWG reconstitution, stakeholder engagement, oversight functions, and code of conduct compliance.

- Government Engagement: Including government oversight of NEITI, policy coordination, and implementation of commitments.

- Industry and Civil Society Engagement: Including participation, representation, and input into EITI processes.

- Transparency Templates: Including systematic disclosures, legal and fiscal frameworks, contracts and licenses, beneficial ownership, state participation, revenue collection, and environmental and social impacts.

- Specific Validation Findings: Including contract disclosure, license register, beneficial ownership, state participation, quasi-fiscal expenditures, infrastructure provisions, and subnational transfers.

- Strategic Priorities: Including energy transition, revenue sustainability, and resource dependence.

2.3 Key Diagnostic Review Themes

Based on the Validation findings and the NSWG's self-assessment requirements, the following thematic areas have been identified for diagnostic review:

| Theme | Description |
| --- | --- |
| MSG Governance and Stakeholder Engagement | Reviews of NSWG composition, functioning, oversight, and stakeholder participation. |
| Legal and Fiscal Framework | Reviews of the legal and fiscal regime governing extractive activities, including reforms and implementation. |
| Contracts and Licensing | Reviews of contract and license allocation, disclosure, and register management. |
| Beneficial Ownership | Reviews of beneficial ownership disclosure, reliability, and integration. |
| State Participation and SOEs | Reviews of state-owned enterprise governance, transactions, and quasi-fiscal expenditures. |
| Revenue Collection and Management | Reviews of revenue collection, disaggregation, timeliness, and data quality. |
| Subnational Contributions | Reviews of subnational payments, transfers, and revenue management. |
| Environmental and Social Impacts | Reviews of environmental and social expenditures, impact assessments, and monitoring. |
| Infrastructure and Barter Arrangements | Reviews of resource-backed loans, infrastructure provisions, and barter-type arrangements. |
| Energy Transition and Revenue Sustainability | Reviews of energy transition policies, revenue sustainability, and resource dependence. |

3.0 GUIDING PRINCIPLES

The following principles shall guide the design, commissioning, and implementation of all diagnostic reviews under this framework:

3.1 Stakeholder Ownership

All diagnostic reviews shall be owned by the NSWG and conducted with the active participation of all stakeholder constituencies i.e., government, industry, and civil society.

3.2 Transparency and Openness

The process for commissioning, conducting, and disseminating diagnostic reviews shall be transparent, with all ToRs, reports, and findings made publicly available.

3.3 Independence and Objectivity

Diagnostic reviews shall be conducted with independence and objectivity, employing appropriate methodologies using external and internal expertise as the need demands.

3.4 Evidence-Based Approach

All diagnostic reviews shall be grounded in evidence, utilising available data, documentation, and stakeholder consultations.

3.5 Action-Oriented

Diagnostic reviews shall produce actionable recommendations that can be implemented to strengthen EITI implementation and extractive sector governance.

3.6 Proportionality

The scope and depth of each diagnostic review shall be proportionate to the significance of the issue and the resources available.

3.7 Integration and Coordination

Diagnostic reviews shall be integrated with NEITI's work planning, reporting, and strategic planning processes to ensure coherence and avoid duplication.

3.8 Continuous Improvement

The framework shall provide for the continuous improvement of diagnostic review processes, incorporating lessons learned and emerging best practices.

3.9 Sustainability

Diagnostic reviews shall be designed to strengthen systematic disclosure and institutional capacity, reducing reliance on one-off EITI reporting.

3.10 Gender and Inclusivity

All diagnostic reviews shall consider gender dimensions and ensure the inclusion of marginalised and affected communities.

4.0 DIAGNOSTIC REVIEW CATEGORIES

Diagnostic reviews under this framework are categorised based on their nature and purpose:

Category A: Governance and Institutional Diagnostics

Purpose: To assess the effectiveness of governance structures, processes, and stakeholder engagement in EITI implementation.

Examples:

- NSWG composition and functioning review.

- Stakeholder engagement and consultation assessment.

- Code of conduct compliance review.

- NEITI Secretariat administration and oversight review.

Category B: Policy and Regulatory Diagnostics

Purpose: To review the adequacy, implementation, and transparency of legal and regulatory frameworks governing the extractive sector.

Examples:

- Legal and fiscal framework review.

- Contract and license allocation practices review.

- Environmental and social regulatory framework review.

- Revenue sharing and distribution framework review.

Category C: Disclosure and Transparency Diagnostics

Purpose: To assess the comprehensiveness, reliability, and timeliness of disclosures required under the EITI Standard.

Examples:

- Systematic disclosure assessment.

- Contract and license disclosure review.

- Beneficial ownership disclosure review.

- Revenue and payment data quality review.

- Subnational transfer and payment review.

Category D: Operational and Financial Diagnostics

Purpose: To review the operations, financial management, and transactions of extractive sector entities.

Examples:

- State-owned enterprise governance and transaction review.

- Quasi-fiscal expenditure review.

- Infrastructure provision and barter arrangement review.

- Resource-backed loan assessment.

Category E: Strategic and Thematic Diagnostics

Purpose: To address emerging issues, strategic priorities, and thematic areas of importance to extractive sector governance.

Examples:

- Energy transition and climate risk assessment.

- Revenue sustainability and resource dependence review.

- Gender and social inclusion in extractive governance.

- Corruption risk assessment.

5.0 DETAILED DIAGNOSTIC REVIEW SCHEDULE

5.1 Priority Ranking

Diagnostic reviews have been prioritised based on:

- Criticality: The importance of the issue to EITI Validation and core governance.

- Urgency: The time sensitivity of the issue, including Validation deadlines.

- Impact: The potential for the review to generate meaningful reform.

- Resource Requirements: The cost and complexity of the review.

- Sequencing: The logical order in which reviews should be conducted.

Priority Levels:

- Priority 1 (High): Reviews essential for addressing Validation corrective actions and core governance issues. To be scheduled in Year 1–2.

- Priority 2 (Medium): Reviews important for strengthening implementation but with longer lead times. To be scheduled in Year 2–3.

- Priority 3 (Standard): Reviews addressing encouraged provisions and strategic priorities. To be scheduled in Year 3–5.

5.2 Diagnostic Review Schedule

The following table sets out the diagnostic reviews to be undertaken, organised by priority and indicative timeline.

PRIORITY 1 DIAGNOSTIC REVIEWS (Year 1–2: 2024–2025)

| S/N | Diagnostic Review Title | Objective | Rationale & Expected Outcomes | EITI Requirement / Validation Finding | Scope & Key Questions | Implementation Approach | Deliverables |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DR1 | NSWG Governance and Functioning Diagnostic | To assess the composition, functioning, and effectiveness of the NSWG and develop recommendations for improvement. | Rationale: Validation identified 17 months' delay in NSWG reconstitution, lack of transparent nomination processes, weaknesses in oversight, and excessive per diem rates. Outcomes: Enhanced NSWG effectiveness, improved stakeholder representation, and strengthened oversight. | Requirement 1.4 | Scope: NSWG composition, nomination processes, meeting frequency and attendance, decision-making, oversight of Secretariat, per diem practices, code of conduct compliance. Key Questions: Is the NSWG constituted in a timely and transparent manner? Are stakeholder groups adequately represented? Does the NSWG exercise effective oversight? | Internal Secretariat review with stakeholder consultations | 1. Diagnostic report on NSWG governance. 2. Recommendations for improving composition, processes, and oversight. 3. Revised NSWG Charter/Board Charter. |
| DR2 | Stakeholder Engagement and Consultation Diagnostic | To assess the effectiveness of stakeholder engagement across all constituencies and identify barriers to participation. | Rationale: Validation identified weaknesses in stakeholder input, lack of regular meetings, inadequate CS representation, and limited industry engagement. Outcomes: Enhanced stakeholder participation, improved consultation processes, and strengthened constituency coordination. | Requirements 1.2, 1.3, 1.4 | Scope: Engagement processes for CSO, industry, and government constituencies; consultation mechanisms; representation and coordination structures. Key Questions: Are stakeholders adequately consulted on EITI processes? Are there barriers to participation? Are constituency coordination mechanisms effective? | External consultant with stakeholder consultations | 1. Stakeholder engagement diagnostic report. 2. Recommendations for improving consultation and participation. 3. Action plan for addressing barriers to participation. |
| DR3 | Contract and License Disclosure Diagnostic | To assess the current status of contract and license disclosure and develop a plan for full compliance. | Rationale: Validation found that oil and gas contracts are not published, and there is no explicit policy on contract disclosure in the mining sector. Outcomes: Full disclosure of contracts and licenses granted or amended from January 2021, and a published plan for comprehensive disclosure. | Requirements 2.2, 2.3, 2.4 | Scope: All active contracts and licenses in oil, gas, and mining sectors; disclosure policies and practices; barriers to disclosure. Key Questions:Which contracts and licenses are currently disclosed? What are the barriers to full disclosure? What plan exists for achieving full disclosure? | Hybrid: Secretariat review with external legal expertise | 1. Diagnostic report on contract and license disclosure. 2. Comprehensive list of all active contracts and licenses. 3. Plan for full contract disclosure with clear timeframes. |
| DR4 | Beneficial Ownership Disclosure Diagnostic | To assess the comprehensiveness, reliability, and timeliness of beneficial ownership disclosures and develop a plan for full compliance. | Rationale: Validation found that some extractive companies have yet to disclose BO, a relatively large number of companies have not published BO data, and there are discrepancies between the NEITI BO Register and the CAC Company Register. Outcomes: Full BO disclosure for all extractive companies, enhanced reliability, and integration of BO registers. | Requirement 2.5 | Scope: BO disclosures for all companies holding or applying for extractive licenses; high-risk companies; PEP disclosures; data reliability mechanisms. Key Questions: Which companies have not disclosed BO? What are the barriers to disclosure? Are PEPs disclosed regardless of ownership level? Are there discrepancies between registers? | External consultant with forensic audit capacity | 1. BO disclosure diagnostic report. 2. Comprehensive BO disclosure assessment. 3. Action plan for achieving full BO disclosure and enhancing reliability. |
| DR5 | State Participation and SOE Governance Diagnostic | To assess the transparency and accountability of state participation, particularly NNPC's operations, transactions, and governance. | Rationale: Validation found that NNPC's AFS does not include financial statements of companies in which NNPC holds majority ownership, NEITI has not consistently tracked changes in NNPC ownership, and there is insufficient transparency in resource-backed loans. Outcomes: Enhanced transparency in SOE governance, improved disclosure of ownership and transactions, and better understanding of quasi-fiscal activities. | Requirements 2.6, 4.5, 6.2 | Scope: NNPC and other SOEs' level of ownership in extractive companies; terms attached to equity interests; resource-backed loans; quasi-fiscal expenditures; corporate governance practices. Key Questions: What are NNPC's ownership levels in extractive companies? What are the terms of resource-backed loans? What expenditures could be considered quasi-fiscal? | Hybrid: Secretariat review with external financial expertise | 1. SOE governance diagnostic report. 2. Assessment of NNPC's ownership and transactions. 3. Recommendations for improving SOE transparency and accountability. |

PRIORITY 2 DIAGNOSTIC REVIEWS (Year 2–3: 2025–2026)

| S/N | Diagnostic Review Title | Objective | Rationale & Expected Outcomes | EITI Requirement / Validation Finding | Scope & Key Questions | Implementation Approach | Deliverables |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DR6 | License Register Diagnostic | To assess the completeness, accuracy, and accessibility of license registers in the oil, gas, and mining sectors. | Rationale: Validation found gaps in information such as date of application and date of award in the mining licence register; the DPR NOGIAR does not provide up-to-date information; NUPRC website publishes license data in a convoluted way; and coordinates of oil and gas licenses are not available. Outcomes: Comprehensive, accurate, and accessible license registers for all sectors. | Requirement 2.3 | Scope: Mining, oil, and gas license registers; completeness of information (license holder, coordinates, dates of application/award/expiry); accessibility and usability. Key Questions: Are license registers complete and accurate? Are they publicly accessible and user-friendly? What gaps exist and how can they be addressed? | Internal Secretariat review with NUPRC and MCO engagement | 1. License register diagnostic report. 2. Gap analysis and recommendations for improvement. 3. Action plan for developing and publishing comprehensive registers. |
| DR7 | Revenue Data Quality and Assurance Diagnostic | To assess the quality, reliability, and assurance of revenue and payment data disclosed under EITI reporting. | Rationale: Validation and self-assessment templates require comprehensive review of data quality, assurance procedures, and audit mechanisms for revenue data. Outcomes: Enhanced reliability of revenue data, strengthened assurance procedures, and improved stakeholder confidence. | Requirements 4.1, 4.9 | Scope: Data quality and assurance procedures for revenue and payment data; audit mechanisms for government entities and companies; reconciliation or risk-based approach. Key Questions: Are revenue data comprehensive and reliable? Are they subject to credible, independent audit? What assurance procedures are in place? | External auditor/consultant | 1. Data quality diagnostic report. 2. Assessment of audit and assurance procedures. 3. Recommendations for strengthening data reliability. |
| DR8 | Subnational Transfers and Payments Diagnostic | To assess the transparency and accountability of subnational transfers and payments related to extractive revenues. | Rationale: Validation found weaknesses in transparency in the management of funds collected by NDDC and NCDMB, insufficient information on financial management of these entities, and lack of publicly accessible comparison of actual transfers with the revenue-sharing formula. Outcomes: Enhanced transparency in subnational revenue management and improved understanding of revenue distribution. | Requirements 4.6, 5.1, 5.2 | Scope: Mandatory and discretionary subnational transfers; revenue-sharing formula; actual vs. expected transfers; NDDC and NCDMB financial management. Key Questions: Are subnational transfers transparent and accountable? Are actual transfers consistent with the revenue-sharing formula? Are NDDC and NCDMB financial reports publicly available? | External consultant with public financial management expertise | 1. Subnational transfers diagnostic report. 2. Assessment of revenue-sharing formula implementation. 3. Recommendations for improving transparency in subnational revenue management. |
| DR9 | Infrastructure Provisions and Barter Arrangements Diagnostic | To assess the transparency of infrastructure provisions, barter arrangements, and resource-backed loans. | Rationale: Validation found insufficient transparency on resource-backed loans and DSDP arrangements, with Project Eagle not disclosing interest rate and loan tenor, and NEITI not having carried out a value-for-money assessment. Outcomes: Enhanced transparency in resource-backed loans and barter arrangements, and value-for-money assessments of such transactions. | Requirement 4.3 | Scope: Resource-backed loans (including Project Eagle); DSDP arrangements; oil-for-product agreements; value-for-money assessments. Key Questions: What resource-backed loans and barter arrangements exist? Are their terms transparent? What is the value-for-money of these transactions? | External consultant with financial and legal expertise | 1. Infrastructure and barter arrangements diagnostic report. 2. Value-for-money assessments of key transactions. 3. Recommendations for improving transparency in such arrangements. |
| DR10 | Quasi-Fiscal Expenditures Diagnostic | To identify and assess quasi-fiscal expenditures by NNPC and other SOEs. | Rationale: Validation found that data on NNPC's deductions is not disaggregated, there is a lack of NEITI analysis of other expenditures that could be considered quasi-fiscal, and the value of NNPC's quasi-fiscal expenditures on fuel subsidies is not published disaggregated by individual fuel marketing company. Outcomes: Identification of quasi-fiscal expenditures, development of a reporting process, and enhanced transparency. | Requirement 6.2 | Scope: NNPC and other SOE spending that could be categorised as quasi-fiscal; fuel subsidies; resource-backed loans; asset transfers. Key Questions: What expenditures by NNPC could be considered quasi-fiscal? Are they transparent and accountable? What reporting process exists for quasi-fiscal expenditures? | Hybrid: Secretariat review with external financial expertise | 1. Quasi-fiscal expenditures diagnostic report. 2. Identification of quasi-fiscal activities. 3. Framework for reporting quasi-fiscal expenditures. |

PRIORITY 3 DIAGNOSTIC REVIEWS (Year 3–5: 2026–2028)

| # | Diagnostic Review Title | Objective | Rationale & Expected Outcomes | EITI Requirement / Validation Finding | Scope & Key Questions | Implementation Approach | Deliverables |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DR11 | Environmental and Social Impact Diagnostic | To assess the adequacy of the regulatory framework and monitoring efforts for environmental and social impacts, and companies' compliance with obligations. | Rationale: Validation found gaps in disclosures of environmental payments and a lack of assessment of companies' compliance with legal and contractual obligations in social and environmental contributions. Outcomes: Enhanced transparency in environmental and social contributions, and improved understanding of companies' compliance. | Requirements 6.1, 6.4 | Scope: Environmental payments mandated by law or contract; social expenditures; companies' compliance with obligations; monitoring and enforcement practices. Key Questions: Are environmental and social payments transparent? Are companies complying with their obligations? Are monitoring and enforcement practices adequate? | External consultant with environmental and social expertise | 1. Environmental and social impact diagnostic report. 2. Assessment of companies' compliance with obligations. 3. Recommendations for improving transparency and accountability. |
| DR12 | Energy Transition and Revenue Sustainability Diagnostic | To assess the implications of the energy transition for Nigeria's extractive sector revenues and develop recommendations for managing revenue sustainability risks. | Rationale: NEITI has launched a framework for climate change accountability, and the Five-Year Strategic Plan identifies energy transition as a strategic priority. Outcomes: Enhanced understanding of energy transition risks and opportunities, and recommendations for revenue sustainability. | Requirements 2.1, 5.3 | Scope: Energy transition commitments, policies, and plans; revenue sustainability; resource dependence; climate risk considerations in forecasting. Key Questions: What are the implications of the energy transition for Nigeria's extractive revenues? What policies are in place to manage revenue sustainability risks? | External consultant with energy and economic expertise | 1. Energy transition diagnostic report. 2. Assessment of revenue sustainability risks. 3. Recommendations for managing the transition. |
| DR13 | Legal and Fiscal Framework Diagnostic | To assess the transparency and effectiveness of the legal and fiscal framework governing extractive activities, including reforms and implementation. | Rationale: The transparency templates require assessment of the legal and fiscal framework, including energy transition commitments, carbon pricing mechanisms, and subsidies. Outcomes: Enhanced understanding of the legal and fiscal framework, and recommendations for reform. | Requirements 2.1, 4.1 | Scope: Legal and fiscal regime; energy transition commitments; carbon pricing mechanisms; subsidies; reforms. Key Questions: Is the legal and fiscal framework transparent and effective? What reforms are underway? Are energy transition commitments reflected in policy? | Internal Secretariat review with legal expertise | 1. Legal and fiscal framework diagnostic report. 2. Assessment of reforms and implementation. 3. Recommendations for strengthening the framework. |
| DR14 | Production and Export Data Diagnostic | To assess the comprehensiveness, reliability, and timeliness of production and export data disclosures. | Rationale: The transparency templates require assessment of production and export data, including methodology, classification standards, and sales volumes and values. Outcomes: Enhanced transparency in production and export data, and improved understanding of sector performance. | Requirements 3.2, 3.3 | Scope: Production and export volumes and values; methodology for calculating data; classification standards; sales volumes and values by project. Key Questions: Are production and export data comprehensive and reliable? Is the methodology for calculating data transparent? Are sales volumes and values disclosed by project? | Internal Secretariat review with data analysis | 1. Production and export data diagnostic report. 2. Assessment of data quality and methodology. 3. Recommendations for improving data transparency. |
| DR15 | Corruption Risk Assessment Diagnostic | To assess corruption risks in Nigeria's extractive sector and develop recommendations for mitigating such risks. | Rationale: EITI encourages the use of diagnostic tools such as NRGI's corruption diagnostic tool. The Validation findings highlight corruption risks in licensing, contracting, and revenue management. Outcomes: Identification of corruption risks and development of mitigation strategies. | Cross-cutting | Scope: Corruption risks in licensing, contracting, revenue collection, and SOE governance; anti-corruption policies and due diligence processes. Key Questions: What are the key corruption risks in Nigeria's extractive sector? Are anti-corruption policies and due diligence processes adequate? | External consultant with anti-corruption expertise | 1. Corruption risk assessment diagnostic report. 2. Identification of key risks and vulnerabilities. 3. Recommendations for mitigating corruption risks. |

5.3 Additional Diagnostic Reviews

The NSWG may, from time to time, identify additional diagnostic reviews required to address emerging issues, new Validation findings, or strategic priorities. The following process shall apply for incorporating additional diagnostic reviews:

- Identification: Any NSWG member or the NEITI Secretariat may propose an additional diagnostic review.

- Justification: The proposer shall provide a justification, including the rationale, scope, and expected outcomes.

- Review: The NSWG shall review the proposal and assess its priority and resource implications.

- Approval: The NSWG shall approve the proposal and incorporate it into the framework.

- Scheduling: The review shall be scheduled within the Five-Year Strategic Plan framework, subject to resource availability.

6.0 IMPLEMENTATION APPROACH

6.1 Governance and Oversight

The NSWG shall provide overall governance and oversight for the implementation of this framework. The NSWG shall:

- Approve the annual diagnostic review work plan.

- Commission diagnostic reviews in accordance with the approved work plan.

- Review and approve diagnostic review ToRs.

- Receive and review diagnostic review reports.

- Consider and approve recommendations arising from diagnostic reviews.

- Monitor the implementation of recommendations.

- Report on progress to stakeholders and the EITI Board.

6.2 Implementation Models

Diagnostic reviews shall be implemented through one of the following models:

| Model | Description | When to Use |
| --- | --- | --- |
| Internal Secretariat Review | Conducted by NEITI Secretariat staff using internal expertise and resources. | For reviews requiring in-depth institutional knowledge and where internal capacity exists. |
| External Consultant | Commissioned from external experts or consulting firms through a competitive procurement process. | For reviews requiring specialised expertise, independence, or where internal capacity is insufficient. |
| Hybrid Model | A combination of internal and external resources, with Secretariat staff providing coordination and context, and external experts providing specialised analysis. | For complex reviews requiring both institutional knowledge and specialised expertise. |

6.3 Procurement and ToR Development

For diagnostic reviews to be conducted by external consultants:

- ToR Development: The NEITI Secretariat, in consultation with the NSWG, shall develop detailed ToRs for each diagnostic review.

- ToR Approval: The NSWG shall review and approve the ToRs.

- Procurement: The NEITI Secretariat shall undertake procurement in accordance with applicable procurement rules and regulations.

- Oversight: The NSWG shall oversee the conduct of the diagnostic review, including reviewing progress reports and providing guidance.

- Quality Assurance: The NSWG shall ensure that diagnostic reviews meet the required quality standards.

6.4 Stakeholder Consultation

All diagnostic reviews shall include appropriate stakeholder consultation, including:

- Government Agencies: Relevant government ministries, departments, and agencies.

- Industry: Extractive companies, industry associations, and relevant unions.

- Civil Society: CSOs, community representatives, and affected groups.

- Expert Input: Subject matter experts and technical advisors as required.

6.5 Reporting and Dissemination

All diagnostic review reports shall be:

- Submitted to the NSWG: For review, discussion, and approval.

- Published: On the NEITI website and other appropriate platforms.

- Disseminated: To stakeholders and the public through appropriate channels.

- Presented: At NSWG meetings and other relevant forums.

7.0 RESOURCE AND FUNDING CONSIDERATIONS

7.1 Resource Requirements

The implementation of this framework requires the following resources:

| Resource Type | Description |
| --- | --- |
| Financial | Budget allocations for external consultants, stakeholder consultations, and report production. |
| Human | NEITI Secretariat staff time for coordination, oversight, and internal reviews. |
| Technical | Access to data, documents, and information required for diagnostic reviews. |
| Institutional | Support from government agencies, industry, and civil society for consultations and data provision. |

7.2 Cost Estimates

Indicative cost estimates for each diagnostic review category:

| Category | Estimated Cost Range | Notes |
| --- | --- | --- |
| Priority 1 Reviews (DR1–DR5) | ₦50–100 million each | Comprehensive reviews requiring external expertise |
| Priority 2 Reviews (DR6–DR10) | ₦30–80 million each | Moderate complexity reviews |
| Priority 3 Reviews (DR11–DR15) | ₦20–50 million each | Variable depending on scope and complexity |

7.3 Funding Sources

Diagnostic reviews shall be funded from:

- NEITI Budget: Annual budgetary allocations from the Federal Government.

- Development Partners: Support from development partners and international organisations.

- Other Sources: Grants, contributions, and other sources as may be identified.

7.4 Resource Mobilisation

The NEITI Secretariat shall:

- Include in Annual Work Plans: All diagnostic reviews scheduled for the year shall be included in NEITI's annual costed work plans.

- Seek Development Partner Support: Approach development partners for technical and financial support.

- Leverage Existing Resources: Utilise existing NEITI resources and expertise where possible.

- Phased Implementation: Implement diagnostic reviews in phases based on resource availability.

8.0 LINKAGES TO NEITI'S FIVE-YEAR STRATEGIC PLAN

8.1 Strategic Alignment

This Diagnostic Review Framework is aligned with NEITI's Five-Year Strategic Plan (2022–2026), which has three major strategic objectives:

- Enhance Extractive Sector Governance Reforms: Through policy research, strategic stakeholder engagement, communication, and inter-agency collaboration.

- Strengthen Institutional Capacity: To deliver on NEITI's mandate effectively and efficiently.

- Promote Transparency and Accountability: In the management of Nigeria's extractive resources.

8.2 Integration with Work Planning

Diagnostic reviews shall be integrated into NEITI's annual costed work plans as follows:

| Year | Diagnostic Reviews Scheduled | Work Plan Integration |
| --- | --- | --- |
| 2024 | DR1, DR2, DR3 | Include in 2024 Annual Work Plan |
| 2025 | DR4, DR5, DR6 | Include in 2025 Annual Work Plan |
| 2026 | DR7, DR8, DR9 | Include in 2026 Annual Work Plan |
| 2027 | DR10, DR11, DR12 | Include in 2027 Annual Work Plan |
| 2028 | DR13, DR14, DR15 | Include in 2028 Annual Work Plan |

8.3 Linkages to Other NEITI Processes

Diagnostic reviews shall be linked to other NEITI processes:

| NEITI Process | Linkage |
| --- | --- |
| EITI Reporting | Diagnostic reviews shall inform the scope and content of EITI reporting. |
| Validation | Diagnostic reviews shall address Validation findings and strengthen future Validation performance. |
| Policy Advocacy | Diagnostic review findings shall inform policy advocacy and reform recommendations. |
| Capacity Building | Diagnostic reviews shall identify capacity gaps and inform capacity-building initiatives. |
| Stakeholder Engagement | Diagnostic reviews shall involve and strengthen stakeholder engagement. |

9.0 MONITORING, EVALUATION, AND REPORTING

9.1 Monitoring Framework

The NSWG shall monitor the implementation of this framework through:

- Quarterly Progress Reports: The NEITI Secretariat shall provide quarterly progress reports to the NSWG.

- Annual Review: The NSWG shall conduct an annual review of the framework's implementation.

- Performance Indicators: Progress shall be measured against agreed performance indicators.

9.2 Performance Indicators

| Indicator | Target | Measurement |
| --- | --- | --- |
| Diagnostic reviews completed | 100% of scheduled reviews | Number of reviews completed vs. planned |
| Recommendations implemented | ≥70% of recommendations | Number of recommendations implemented vs. total |
| Stakeholder satisfaction | ≥80% satisfaction | Stakeholder surveys |
| Validation findings addressed | All corrective actions addressed | EITI Validation assessment |

9.3 Reporting

The NEITI Secretariat shall report on the implementation of this framework through:

- Annual Progress Reports: Including progress on diagnostic reviews.

- Validation Reports: Demonstrating progress in addressing Validation findings.

- NSWG Meeting Reports: Regular updates to the NSWG.

- Public Reports: Published on the NEITI website.

10.0 FRAMEWORK FLEXIBILITY AND AMENDMENTS

10.1 Flexibility

This framework is designed to be flexible and adaptable to changing circumstances. The following provisions ensure flexibility:

- Phased Implementation: Diagnostic reviews shall be implemented in phases based on resource availability.

- Priority Adjustments: The NSWG may adjust priorities based on emerging needs.

- Additional Reviews: The NSWG may add new diagnostic reviews as needs arise.

- Scope Adjustments: The NSWG may adjust the scope of diagnostic reviews based on experience and learning.

10.2 Amendment Procedure

This framework may be amended by the NSWG through the following procedure:

- Proposal: Any NSWG member or the NEITI Secretariat may propose an amendment.

- Justification: The proposer shall provide a justification for the amendment.

- Review: The NSWG shall review the proposal and assess its implications.

- Approval: The NSWG shall approve the amendment by consensus or, failing consensus, by a two-thirds majority vote.

- Documentation: The amendment shall be documented and incorporated into the framework.

10.3 Review and Update

This framework shall be reviewed and updated:

- Annually: As part of the NSWG's annual review of EITI implementation.

- Post-Validation: Following each Validation exercise, to incorporate new findings.

- Strategic Plan Updates: When NEITI's Five-Year Strategic Plan is updated.

- As Needed: When significant changes occur in the EITI Standard or Nigeria's extractive sector.

11.0 NSWG REVIEW, DELIBERATION, AND APPROVAL

11.1 NSWG Deliberation

The NSWG has considered, deliberated on, and approved the proposed diagnostic reviews contained in this framework. The NSWG's deliberations included:

- Review of Validation Findings: Detailed review of the Validation report and corrective actions.

- Assessment of Diagnostic Needs: Identification of diagnostic reviews required to address Validation findings.

- Prioritisation: Assessment of the priority of each diagnostic review based on criticality, urgency, and impact.

- Resource Implications: Consideration of the resource requirements and funding implications.

- Strategic Alignment: Assessment of alignment with NEITI's Five-Year Strategic Plan.

- Implementation Approach: Consideration of the most appropriate implementation model for each diagnostic review.

11.2 NSWG Decision

The NSWG has resolved that:

- Approval: The Diagnostic Review Framework, including the proposed diagnostic reviews, is hereby approved.

- Implementation: Implementation of the diagnostic reviews shall proceed as resources become available.

- Commencement: Implementation is expected to commence from the 2024 financial year onwards.

- Funding: The NEITI Secretariat shall seek to mobilise resources for the implementation of the diagnostic reviews.

- Work Planning: The diagnostic reviews shall be integrated into NEITI's annual costed work plans as appropriate.

- Reporting: The NEITI Secretariat shall report regularly to the NSWG on the implementation of the framework.

- Flexibility: The NSWG may adjust the framework as needed to respond to emerging issues and changing circumstances.

11.3 Sign-Off

On behalf of the National Stakeholders' Working Group (NSWG):

| Name | Position | Signature | Date |
| --- | --- | --- | --- |
|  | Chair, NSWG |  |  |
|  | Government Representative |  |  |
|  | Industry Representative |  |  |
|  | Civil Society Representative |  |  |
|  | Executive Secretary, NEITI |  |  |

12.0 ANNEXES

Annex A: Glossary of Terms

| Term | Definition |
| --- | --- |
| Diagnostic Review | A systematic assessment of a specific issue, process, or system to identify strengths, weaknesses, and areas for improvement. |
| Multi-Stakeholder Group (MSG) | The body responsible for overseeing EITI implementation in a country, comprising government, industry, and civil society representatives. |
| National Stakeholders' Working Group (NSWG) | Nigeria's multi-stakeholder group for EITI implementation. |
| Validation | The EITI's quality assurance mechanism, assessing a country's implementation of the EITI Standard. |
| Corrective Action | A specific action required to address a shortcoming identified in Validation. |
| Systematic Disclosure | The regular, routine publication of information by government agencies and companies, without the need for EITI reporting. |

Annex B: Summary of Diagnostic Reviews

| # | Diagnostic Review Title | Priority | Indicative Timeline | Estimated Cost |
| --- | --- | --- | --- | --- |
| DR1 | NSWG Governance and Functioning Diagnostic | Priority 1 | Year 1 (2024) | ₦xx million |
| DR2 | Stakeholder Engagement and Consultation Diagnostic | Priority 1 | Year 1 (2024) | ₦xx million |
| DR3 | Contract and License Disclosure Diagnostic | Priority 1 | Year 1–2 (2024–2025) | ₦xx million |
| DR4 | Beneficial Ownership Disclosure Diagnostic | Priority 1 | Year 2 (2025) | ₦xx million |
| DR5 | State Participation and SOE Governance Diagnostic | Priority 1 | Year 2 (2025) | ₦xx million |
| DR6 | License Register Diagnostic | Priority 2 | Year 2-3 (2025-2026) | ₦xx million |
| DR7 | Revenue Data Quality and Assurance Diagnostic | Priority 2 | Year 2-3 (2025-2026) | ₦xx million |
| DR8 | Subnational Transfers and Payments Diagnostic | Priority 2 | Year 3 (2026) | ₦xx million |
| DR9 | Infrastructure Provisions and Barter Arrangements Diagnostic | Priority 2 | Year 3 (2026) | ₦xx million |
| DR10 | Quasi-Fiscal Expenditures Diagnostic | Priority 2 | Year 3 (2026) | ₦xx million |
| DR11 | Environmental and Social Impact Diagnostic | Priority 3 | Year 4 (2027) | ₦xx million |
| DR12 | Energy Transition and Revenue Sustainability Diagnostic | Priority 3 | Year 4 (2027) | ₦xx million |
| DR13 | Legal and Fiscal Framework Diagnostic | Priority 3 | Year 4-5 (2027-2028) | ₦xx million |
| DR14 | Production and Export Data Diagnostic | Priority 3 | Year 5 (2028) | ₦xx million |
| DR15 | Corruption Risk Assessment Diagnostic | Priority 3 | Year 5 (2028) | ₦xx million |

Annex C: Template for Diagnostic Review Terms of Reference

NEITI Diagnostic Review -Terms of Reference

1. Title:

2. Background and Rationale:

3. Objective:

4. Scope of Work:

5. Key Questions:

6. Methodology:

7. Deliverables:

8. Timeline:

9. Qualifications:

10. Reporting:

11. Budget:

12. Approval: