## Sheet1
THE REVISED NIGERIA EITI 2024 APPROVED COUNTRY WORK PLAN FINANCIALS
FUNDING
Strategic Objectives | Workplan Objectives | Act Nrb | Activities | Total Cost (Naira) | Timeline | FGN | Donor | Short fall | Responsible Organization/Department | Output | Expected Outcome | Outcome Indicator
OBJECTIVE 1: Strengthen extractive sector governance and reforms through policy research, strategic stakeholder engagement, communication, and inter-agency collaboration | Improve extractive industries' governance and anti-corruption initiatives through policy research and engagements | 1 | Production of NEITI FAAC Quarterly Review on Federation Revenue Allocation (Q4, 2023-Q3, 2024) | 6700000 | Mar- Dec | 6700000 |  |  | PPS/ Energy & Mining/Comms | Four (4) Quarterly FAAC Reports | Stakeholder Engagements and public debate on Federation Account revenue and disbursements | News report, media mentions, literature reference of NEITI Quarterly Review
|  | 1.01 | Study on PMS pricing, cost recovery and Domestic Crude Allocation (DCA) remittances to the Federation Account | 7000000 | Mar -Jul | 7000000 |  |  | PPS/ Energy & Mining | Report of findings and recommendations on PMS pricing and NNPC remittances to the Federation Account | Stakeholder Engagement and Policy review on management of DCA | News reports, media mentions, stakeholder engagement etc on PMS pricing and management of DCA
|  | 1.02 | Conduct Study on Artisanal Small Scale Miners (ASMs) | 20000000 | Jun-Aug | 20000000 |  |  | PPS / Energy & Mining | Draft Report |  | Final Artisanal Small Scale Miners Report
|  | 1.03 | Conduct Study on Minerals Buying Centers | 20000000 | Jun-Aug | 20000000 |  |  | PPS / Energy & Mining | Draft Report |  | Final Mineral Buying Centers Report
|  | 1.04 | Conduct Study on mineral beneficiation | 15000000 | Jun - Sep | 15000000 |  |  | PPS / Energy & Mining | Draft Report |  | Final beneficiation impact report
|  | 1.05 | Conduct Corruption Risk Assessment in the Oil, Gas and Mining Sector. | 100000000 | May-Jul 24 |  | 100000000 |  | ICPC |  | Number of compliance recommendations that are fully implemented to eliminate corruption loopholes/vulnerabilities in the sector.
|  | 1.06 | Conduct System Study and Review in the Oil, Gas and Mining Sector. | 100000000 | Sept-Oct 24 |  | 100000000 |  | ICPC |  | Number of compliance recommendations that are fully implemented to eliminate corruption loopholes/vulnerabilities in the sector. Improve service delivery and enhance revenues in the sector
|  | 1.07 | Scoping study for the Oil and Gas Sector | 5000000 | Jan-Feb | 5000000 |  |  | PPS / Energy & Mining | Draft Scoping Report - Oil and Gas | Enhanced Reporting Framework, established process for ensuring data reliability and a streamlined Exemption Management framework for the review period | Approved scoping report on Oil & Gas Sector
|  | 1.08 | Scoping study for the Solid Mineral Sector | 5000000 | Jan-Feb | 5000000 |  |  | PPS / Energy & Mining | Draft Scoping Report - SM | Enhanced Reporting Framework, established process for ensuring data reliability and a streamlined Exemption Management framework for the review period | Approved scoping report on the Solid Minerals Sector
|  | 1.09 | Scoping study for Extractive Revenue Management (FASD) | 5000000 | Jan-Feb | 5000000 |  |  | PPS / Energy & Mining | Draft Scoping Report - FASD | Enhanced Reporting Framework, established process for ensuring data reliability and a streamlined Exemption Management framework for the review period | Approved scoping report for FASD
|  | 1.1 | Policy Dialogue on the Impact of the 13% derivation in the oil producing states | 6000000 | Mar - Jun |  | 6000000 |  | PPS / Energy & Mining | Report of the policy dialogue, participants list | Informed citizenry on the utilization of 13% derivation. | Citizens advocacy and media reports on the utlization of 13% derivation.
|  | 1.11 | Conduct status update of remedial issues for 2020 and 2021 NEITI industry reports | 10000000 | Aug - Nov | 10000000 |  |  | Remediation Unit | Report on the implementation status of 2020 and 2021 NEITI industry audit recommendations | Gradually reducing established gaps in the extractive sector through startegic engagement, capacity building, operations reorientation and administrative procedure change | Updated remedial issues template containing status of issues from previous reports including actions by stakeholders and their outcomes.
| Broaden and deepen stakeholder engagement in the NEITI process through strategic communication | 1.12 | Review and update stakeholder's map. | 3500000 | Jan-Mar (Jun - Sep) | 3500000 |  |  | COMMS | Revised stakeholder map | Well informed Stakeholders. | Stakeholders Map developed
|  | 1.13 | Impact of Energy Transition on Nigeria's Economy | 26000000 | May-Oct |  | 26000000 |  | PPS/ Energy and Mining/ Ford Foundation
|  | 1.14 | Review of the institutional and governance framework of the Solid Mineral Sector with a focus in Critical Minerals | 26000000 | May-Oct |  | 26000000 |  | PPS/ Energy and Mining/ Ford Foundation
|  | 1.15 | Conduct engagements with relevant government agencies on Energy Transition | 7500000 | Nov |  | 7.500,000 |  | PPS/ Energy and Mining/ Ford Foundation
|  | 1.16 | Conduct engagements with extractive companies on Energy Transition | 7500000 | Nov |  | 7.500,000 |  | PPS/ Energy and Mining/ Ford Foundation
|  | 1.17 | Conduct engagement with stakeholders on EITI Standards (CSO, media , staff etc) | 9000000 | Jun-Jul | 9000000 |  |  | COMMS/PPS/ Energy and Mining |  | Broadened stakeholders Knowledge and understanding on Energy transition. | Participants list. Media mention and programme report.
|  | 1.18 | Commemorate International Women’s Day | 1800000 | Jan-Mar | 1800000 |  |  | COMMS/PPS |  | Increased women participation in the extractive sector. Improved public understanding on gender equity and inclusion the extractive industries. | Media reports. Release of the report. Participants list Programme report.
|  | 1.19 | Conduct Round table with relevant Government Agencies on Environmental Sustainability climate change and global warming | 7000000 | Oct-Nov | 7000000 |  |  | COMMS/PPS/ Energy and Mining | Draft Reports | Policy measures on mitigating climate change, global warming. Increased knowledge on climate change and global -warming issues. Sustained public campaign and awareness against climate change and global warming. | Media Mentions Participants list Programme report.
|  | 1.2 | Develop framework for stakeholders’ Engagement. |  | Jan-Mar |  | DONOR |  | COMMS | Stakeholder engagement framework | Stakeholders with adequate knowledge of NEITI/ EITI Process | Framework for engaging with different stakeholders developed.
|  | 1.21 | *Organise stakeholders' capacity building workshops on NEITI reports and other identified industry Issues. | 30000000 | Jan-DEC | 30000000 |  |  | COMMS | Report of the capacity building | Improved public understanding of NEITI Process | Number of participants trained. Number of capacity building workshop held.
|  | 1.22 | Identify programs by strategic organizations for collaborations and strategic partnerships eg. NESG, Nigerian Mining Week, NAEC, Mining Indaba | 6000000 | Jan-DEC | 6000000 |  |  | COMMS | Report of collaborative programs | Strategic partnerships/ collaborations built with credible and reputable Association for increased visibility and relevance of NEITI | Number of strategic partnerships and events held
|  | 1.23 | Videographs on -Who we are. -Health & Safety. | 5000000 | March | 5000000 |  |  | COMMS | Copies of the videographs produced | Well Informed Stakeholders with adequate knowledge of NEITI/ EITI Process. | Videograph on Who we Are and Health and Safety produced
|  | 1.24 | Quarterly NEITI House Dialogue Series-Topical issues on Natural Resource governance |  | Jan-Dec |  | DONOR |  | COMMS/PPS/E&M | Report of the NEITI House Dialogue | Well informed Stakeholders with adequate knowledge of the ongoing reforms in the extractive sector | Number of Dialogue held
|  | 1.25 | Conduct public enlightenment program- Roadshows, Townhall Meetings, outreaches and education of stakeholders through traditional media programmes such as editorials, features and Op-ed: Jingles, Commercials and social media campaigns. etc. at the Sub-national level (6 geo-political zones). | 6000000 | Jan-Dec | 6000000 |  |  | COMMS | Report of the event | Well informed Stakeholders with adequate knowledge of the extractive sector | Number of events held and number of participants.
|  | 1.26 | Content management of NEITI website and social media platforms |  | JAN-DEC |  |  |  | COMMS | Updaed website | Well informed Stakeholders with adequate knowledge of the extractive sector | Number of visits to the website and followership on NEITI Official platform.
|  | 1.27 | Publish information and data through digital portals created by NEITI |  | Jan-Dec |  |  |  | COMMS | Information and data published, media report | Timely disclosure of information and data across the extractive value chain. | Number of Reports published
|  | 1.28 | Quarterly engagements with stakeholders | 5000000 | Jan-Dec | 5000000 |  |  | COMMS | Attendance list | Well informed Stakeholders with adequate knowledge of the extractive sector. | Number of Press Briefing held.
| Increase public access and understanding of NEITI reports, policy briefs and knowledge products through effective dissemination | 1.29 | Develop and produce IEC materials for stakeholders engagement. |  | Jan-DEC |  | DONOR |  | COMMS | Specific publications | Increased public access to NEITI Reports | Number of publications produced.
|  | 1.3 | Simplification of NEITI industry reports- 2022 & 2023-Oil, gas, Mining and FASD through videography, animations, cartoons, and infographics for better understanding. |  | Jan-Dec |  | DONOR |  | COMMS | Simplified version of the reports | Stakeholders with adequate knowledge of global trends in the extractive sector | Number of simplified reports.
|  | 1.31 | Public presentation of NEITI presentation. |  | Jan-DEC |  | DONOR |  | COMMS | Report of the public presentation | Stakeholders with adequate knowledge of global trends in the extractive sector | Number of public presentations held and attendance at the presentations.
| Facilitate timely implementation of extractive industries audit recommendations through effective inter-agencies collaboration | 1.32 | Round table meetings with Anti-Corruption Agencies on the enforcement of findings and recommendations from NEITI Audit reports | 5000000 | Jan-Dec | 5000000 |  |  | LEGAL | Minutes of meetings | Improved synergy with ACAs on the implementation of NEITI audit recommendations and findings | Number of issues, cases and investigations initiated/resolved by ACAs
|  | 1.33 | Provide support to the re-activation and strengthening of Inter-Ministerial Task Team (IMTT). |  | Jan-DEC |  | DONOR |  | COMMS | Report of the meetings | Sustained engagement with relevant agencies and Stakeholders are equipped with adequate knowledge of the ongoing reforms in the extractive sector | Number of meetings held with high level participation.
|  | 1.34 | Conduct policy dialogues on the findings and recommendations contained in the NEITI researches and knowledge products | 15000000 | Jan-Dec | 15000000 |  |  | PPS/COMMS | Report of the policy dialogue | Well informed Stakeholders with adequate knowledge of the ongoing reforms in the extractive sector | Number of Dialogues held.
| To monitor and evaluate governance and anti-corruption initiatives at all levels of governance and provide data-based coordination | 1.35 | Research Studies of Anti-Corruption and Governance Initiatives | 20,000.000.00 | Q1-Q4 | 20,000.000.00 |  |  | TUGAR |  | Increased data available for better coordination and implementation of anti-corruption and governance initiatives | Consult procured, Updated report, Launch of report.
| To monitor and evaluate governance and anti-corruption initiatives and provide data-based coordination | 1.36 | Follow up activities on TI-CPI analysis and the implementation of Executive Order 1 | 12000000 | Feb-Dec | 12000000 |  |  | TUGAR |  | Reduction of corruption and improved transparency in the sector. Improved implementation of Executive Order 1 | Report and findings
| This project aims at enabling a better understanding of the Codes of Conduct for Public Officers for implementation and enforcement. To assist in the implementation of the codes and serve as a framework for sustainable preventive mechanisms | 1.37 | Implementation of findings of Scoping Survey and Gap analysis of the Ethics Framework in Nigeria – Follow up activities | 5000000 | Q1-Q4 | 5000000 |  |  | TUGAR |  | Better understanding of the codes of conduct for public officers for implementation and enforcement | CCB Officials trained on the use of the interactive learning tool. Certified Public Officers on the online training on the Explanatory Manual for Public Officers.
| The main goal of the NACS is to remove hindrances to transparency and accountability in public institutions and government systems. Strengthen mechanisms and ensure service delivery to the citizens | 1.38 | Implementation of the National Anti-Corruption Strategy (Monitoring and Evaluation) | 5000000 | Jan-Dec | 5000000 |  |  | TUGAR |  | Evaluation report on implementation of NACS 2017 - 2021 and baseline for commencement of new phase of the NACS | Consultant procured. Reports of meetings and surveys. Evaluation report
| To support the new developments and achievements in the Nigeria Ports with empirical data | 1.39 | Corruption Risk Assessment in the Nigerian Ports – Implementation of the Integrity Plan. | 2000000 | Jan-Dec | 2000000 |  |  | TUGAR |  | Supporting the achievements in the ports with empirical data | Report of meetings
| Facilitate the building of synergy among diverse anti-corruption initiatives | 1.41 | Coordination of the Anti-Corruption Agencies on the platform of the IATT | 5000000 | Jan-Dec | 5000000 |  |  | TUGAR |  | Greater cooperation and synergy amongst the ACAs. | Reports
| Facilitate the building of synergy among diverse anti-corruption initiatives | 1.42 | Joint commemoration of the International Anti-Corruption Day | 2000000 | Aug-Dec 24 | 2000000 |  |  | TUGAR |  | Improved synergy and inter agency cooperation and collaboration | Report, Action plan
| Facilitate the building of synergy among diverse anti-corruption initiatives | 1.43 | Joint commemoration of the African Anti-Corruption Day | 1000000 | Feb-July 24 | 1000000 |  |  | TUGAR |  | Improved synergy and inter agency cooperation and collaboration | Report, Action plan
| Objective 1 Total |  |  | 492000000 |  | 219000000 | 258000000
|  | 2 | Oil and gas Audit 2022 - 2023 | 79000000 | 2024-05-02 | 79000000 |  |  | Energy & Mining |  |  | NSWG Approved Oil & Gas Report 2022-2024
|  | 2.01 | IA Pre-Engagement Workshop - Oil and Gas | 800000 | 2024-02-01 | 800000 |  |  | Energy & Mining | Draft Report | 1. Clarified roles and expectations between IA and NEITI. 2. Improved data reliability. | IA engagement report
|  | 2.02 | IA Pre-Engagement Workshop - Soild Mineral | 800000 | 2024-02-01 | 800000 |  |  | Energy & Mining | Draft Report | 1. Clarified roles and expectations between IA and NEITI. 2. Improved data reliability. | IA engagement report
|  | 2.03 | IA Pre-Engagement Workshop - FASD | 500000 | 2024-03-01 | 500000 |  |  | Energy & Mining | Draft Report | 1. Clarified roles and expectations between IA and NEITI. 2. Improved data reliability. | IA engagement report
|  | 2.04 | Create, amend and update data collection template to collect data/information that aligns with 2023 EITI standard requirements for oil and gas | 3000000 | 2024-03-01 | 3000000 |  |  | Energy & Mining | Draft Templates | Comprehensive data collections templates that are precise updated to capture regulatory changes and emerging data needs. | Approved reviewed and updated Oil & Gas Data templates
|  | 2.05 | Create, amend and update data collection template to collect data/information that aligns with 2023 EITI standard requirements – SOLID MINERAL | 3000000 | 2024-03-01 | 3000000 |  |  | Energy & Mining | Draft Templates |  | Approved reviewed and updated Solid Minerals templates
|  | 2.06 | Create, amend and update data collection template to collect data/information that aligns with 2023 EITI standard requirements -FASD | 4000000 | 2024-03-01 | 4000000 |  |  | Energy & Mining | Draft Templates |  | Approved reviewed and updated FASD templates
|  | 2.07 | Workshop with Oil & gas companies on EITI Standard | 5000000 | 2024-03-01 | 5000000 |  |  | Energy & Mining | Draft Report | A shared understanding with critical stakeholders on requirements of the 2023 EITI standard and Nigeria's upcoming validation with the EITI | Reports
|  | 2.08 | Workshop with solid minerals companies on EITI standard | 5000000 | 2024-03-01 | 5000000 |  |  | Energy & Mining | Draft Report |  | Reports
|  | 2.09 | States and Beneficiary agencies engagement on 2023 EITI Standard | 4000000 | 2024-05-01 | 4000000 |  |  | Energy & Mining | Draft Report |  | Engagement Report
|  | 2.1 | Template Workshop O &G | 7000000 | 2024-03-01 | 7000000 |  |  | Energy & Mining | Draft Report | Draft Report | Workshop Report
|  | 2.11 | Template Workshop – Solid Minerals | 20000000 | 2024-03-01 | 20000000 |  |  | Energy & Mining | Draft Report | Draft Report | Workshop Report
|  | 2.12 | Template Workshop - FASD | 4000000 | 2024-03-01 | 4000000 |  |  | Energy & Mining | Draft Report | Draft Report | Workshop Report
|  | 2.13 | Update and disclose Templates (e.g., EITI Summary Data, Transparency and other relevant templates) | 1000000 | 2024-12-01 | 1000000 |  |  | Energy & Mining | Draft completed templates | Draft updated templates | Updated and accessible oil, gas and solid mineral sector data and information
|  | 2.14 | Data collection | 7000000 | May-Jun 2024 | 7000000 |  |  | Energy & Mining |  | Comprehensive data and information for analysis in preparation of relevant reports | Unreconciled data report
|  | 2.15 | Reconcilliation meeting - O&G | 7000000 | Jul 24 | 7000000 |  |  | Energy & Mining |  | • Summary of differences for individual entities • Sign-Off with individual entities | • Summary of differences for individual entities • Sign-Off with individual entities
|  | 2.16 | FASD Audit 2022-2023 | 60000000 | Jul-Aug 24 | 60000000 |  |  | Energy & Mining |  |  | NSWG Approved FASD Report 2022-2023
|  | 2.17 | Data collection | 10000000 | Apr-24 | 10000000 |  |  | Energy & Mining | Populated templates | Comprehensive data and information for analysis in preparation of relevant reports | Unreconciled data report
|  | 2.18 | Project visits to validate data/information received from beneficiary agencies - FASD | 4500000 |  | 4500000 |  |  | Energy & Mining | Draft Reports | Bilateral engagement reports (beneficiary agencies and selected states) | Engagement reports
|  | 2.19 | Resource Disbursement Meetings | 2000000 | Jan - Dec 24 | 2000000 |  |  | Energy & Mining | * Monthly FAAC Meetings Reports * Monthly Post Mortem Meetings Reports. * Monthly PRM&RC Meetings Reports. * Monthly FRRC Meetings Reports. | Enhanced transparency in the administration of extractive revenue and its allocation, ensuring improved accessibility for stakeholders, including Civil Society Organizations (CSOs), Community-Based Organizations (CBOs), development partners, and the general public. | * Timely Population of FAAC Templates. * Accurate Data * Availability and Accessibility of resource generation, allocation and disbursement information.
|  | 2.2 | Solid Minerals Audit 2022-2023 | 36000000 | May-Jun 24 | 36000000 |  |  | Energy & Mining |  |  | NSWG Approved Solid Minerals Report
|  | 2.21 | Data collection | 20000000 | 2024-07-01 | 20000000 |  |  | Energy & Mining | Populated templates | Comprehensive data and information for analysis in preparation of relevant reports | Unreconciled data report
|  | 2.22 | Reconcilliation meetings in 3 geographical zones | 16000000 | 2024-08-01 | 16000000 |  |  | Energy & Mining | Draft Reports | • Summary of differences for individual entities • Sign-Off with individual entities | Final Reconciliation Report
|  | 2.23 | Update of NEITI Data Dashboard | 2000000 | Jan-Dec 24 | 2000000 |  |  | ICT |  |  | Update of NEITI Data Dashboard
|  | 2.24 | Conduct a round table to evaluate the implementation of the NAMS pilot phase with participating entities and ready the activation and deployment of the NAMS portal for the upcoming 2023-2023 oil and gas industry data collection portal. | 3000000 | 2024-02-01 | 3000000 |  |  | Energy & Mining |  | Draft NAMS implementation evaluation report | Final NAMs implementation assessment and upgrade report
|  | 2.25 | Conduct a field assessment of solid mineral companies across three geographical zones to assess their readiness for integration into the NAMS data collection portal. | 45000000 | 2024-03-01 | 45000000 |  |  | Energy & Mining |  | Draft readiness Report | Final readiness report
|  | 2.26 | Organize capacity building exercises for external and Internal stakeholders | 12000000 | 2024-03-02 | 12000000 |  |  | Energy & Mining/ HR |  | Draft report. | Capacity building report
|  | 2.27 | Secure IT support to scale up and enhance the capacity of the NAMS platform based on feedback from the pilot phase review, and execute necessary deployment updates. | 5000000 | 2024-04-01 | 5000000 |  |  | Energy & Mining |  | Draft report. | Final upgrade report
|  | 2.28 | Conduct 3 rounds of data collation, cleaning and sorting exercises for use in the update of the NEITI dashboard, BO Portal and contextual information of the NEITI website. | 7500000 | Jan - Dec 24 | 7500000 |  |  | Energy & Mining |  | Updated NEITI data DashBoard and BO Portal | Updated NEITI data DashBoard and BO Portal
|  | 2.29 | Implement Remediation plan | 9000000 | Jan - Dec 24 | 9000000 |  |  | Energy & Mining |  | Availability and Accessibility of EITI Information & Data | Implementation Progress Report
|  | 2.3 | Conduct Gap Analysis for Systematic Disclosure Compliance | 15000000 | Mar-Jun 24 |  | 15000000 |  | Energy & Mining |  | Action Plan and implemenatble Strategies | Systematic Disclosure Compliance Report
|  | 2.31 | Implementation of Outcome from Systematic Disclosure Compliance | 15000000 | Jul-Aug 24 |  | 15000000 |  | Energy & Mining |  | Draft implementation progress report | Final Implementation Progress Report
| Increase the impacts and relevance of NEITI by focusing on national and international priorities | 2.32 | Engage Extractive Sector Companies on the status of their Anti-Corruption Policies | 15000000 | Aug-Sept 24 |  | 15000000 |  | Energy & Mining | Status Report | Enhanced adherence to EITI guidelines regarding the disclosure of anticorruption policies by extractive companies, fostering improved compliance within the sector | Number of companies with publicly disclosed anticorruption policy
|  | 2.33 | Review existing regulations in the extractive industries for gender mainstreaming and gender inclusion in the extractive value chain. | 10000000 | Apr-Jul 24 | 10000000 |  |  | PPS/ Energy and Mining | Report of findings and recommendations to update existing laws, regulations and policies to facilitate gender mainstreaming in the extractive industry. | Strengthened legal and institutional framework for gender inclusion in the extractive industry. | Updated laws, policies and regulation on gender equity in the extractive sector.
|  | 2.34 | Review existing Environmental regulations in the Extractive Industries. | 12000000 | Apr-Jul 24 | 12000000 |  |  | PPS/ Energy and Mining | Report of findings and recommendations to update existing laws, regulations and policies to facilitate environmental reporting in the extractive industry. | Strengthened legal and institutional framework for environmental reporting in the extractive industry. | Policies, laws and regulations reviewed.
| To conduct impact analysis and construct country specific indicators and tools for governance and anti-corruption monitoring and reporting | 2.37 | Review of Nigeria’s Implementation of the UNCAC | 8000000 | Apr-Dec 24 | 8000000 |  |  | TUGAR |  | Greater cooperation and synergy amongst the ACAs | Country report and action plan. Reports from CoSP and IRG meetings. Report of meetings
|  | Objective 2 Total |  | 458100000 |  | 413100000 | 45000000 | 0
OBJECTIVE 3:Achieve operational excellence in implementing NEITI mandate through Professionalism, innovation, use of technology, resource management, and capacity building. | Optimize efficiency and effectiveness in NEITI operations through effective human & material resources management, planning, monitoring & evaluation. | 3 | Develop and publish the 2023 Annual Progress Report (APR). | 6000000 | Apr-May | 6000000 |  |  | PPS | 2023 Nigeria Annual (EITI) Annual Progress Report, Publicly accessible documentation of stakeholders participation in APR development | 2025 Nigeria country workplan developed by stakeholders to address challenges and increase outcomes and impact of EITI implementation in Nigeria | 2025 country workplan reflects activities to address gaps and improve future outcomes and impact
|  | 3.01 | Develop and publish the 2025 Annual Country Work Plan. | 6000000 | OCT-NOV 24 | 6000000 |  |  | PPS | • Annual Country Work plan. • Populated 2025 work plan templates by stakeholders. • Report of stakeholder engagement including participants list | *Coordinated implementation of EITI in Nigeria *Donor commitments and partnerships in implementation of country workplan activities | MOUs, letters and reports of collaboration and partnership in the implementation of EITI activities.
|  | 3.02 | Develop and publish the 2024 Annual Work Plan. | 3000000 | JUN-JUL 24 | 3000000 |  |  | PPS | *The mid-year 2024 country work plan review. *Revised 2024 country work plan *Workplan mid-year populated templates by the stakeholders. | *Improved processes of implementing the NEITI work plan.
|  | 3.03 | Develop and publish the Monitoring & Evaluation(M&E) framework for the NEITI 2022-2026 Strategic plan. | 20000000 | Aug 2023 -Apr 2024 |  | 20000000 |  | PPS | *The Monitoring & Evaluation (M&E) Framework For the NEITI 2022 – 2026 Strategic Plan. *80 NEITI staff and stakeholders trained to monitor and evaluate EITI implementation in Nigeria. | Clear measurable indicators for accessing the implementation of the strategic plan. The mid-term and final workplan evaluation, annual progress and strategic plan review reports based on the NEITI M&E framework.
|  | 3.04 | Conduct mid-term review of the implementation of NEITI 2022-2026 strategic plan. |  | Aug-Sept 24 |  | 15000000 |  | PPS | NEITI Strategic Plan midterm review report. | *The revised NEITI 2022 -2026 Strategic Plan.
|  | 3.05 | Develop and publish the Monitoring & Evaluation exercise of the 2023 work plan. | 2000000 | Jan-Apr24 | 2000000 |  |  | PPS | *Monitoring and Evaluation report *Populated template data by the stakeholders. *Populated templates by the stakeholders | High rate of workplan activities implementation.
|  | 3.06 | Conduct regular monitoring of all NEITI’s programs and activities. | 10000000 | Jan-Dec 24 | 10000000 |  |  | PPS | *Activity monitoring reports. *Participants list *Media list
|  | 3.07 | Provision of solar energy as alternate to AEDC Supplies | 12000000 | 2024-04-01 | 12000000 |  |  | ESO/HRA | Solar power equipments | Alternative power supplies | Solar equipments
|  | 3.08 | Purchase of higher capacity generator | 15000000 | 2024-06-01 | 15000000 |  |  | ESO/HRA | Higher capacity generator | Alternative power supplies | Power supplies
|  | 3.09 | Purchase of energy saving security lights | 4500000 | 2024-02-01 | 4500000 |  |  | ESO/HRA | Energy saving bulbs and flourcents | Secured environment both day & night | Well litted premises at night
|  | 3.1 | Maintenance of Electricals,Air- Conditioners,Plumbing,Water Dispensers facilities e,t,c | 18000000 | Jan- Dec 24 | 18000000 |  |  | ESO/HRA | Maintenance of Electricals,Air- Conditioners,Plumbing facilities | functional office facilities | functional office facilities
|  | 3.11 | Maintenance of Elevator | 6500000 | Jun-Nov 23 | 6500000 |  |  | ESO/HRA | Elevator | Monthly assessment reports. | Safe and functional elevator
|  | 3.12 | Re-painting of the Offices | 8500000 | Jan-Feb 24 | 8500000 |  |  | ESO/HRA | Painted offices. | Clean working enviroment | Dirts free office walls
|  | 3.13 | Re-piping of ES, CD(ESO), Finance, EMRD toilet wings. | 7600000 | 2024-02-01 | 7600000 |  |  | ESO/HRA | Re-piped toilet waste pipes | Clean working enviroment | Clean toilet facilities
|  | 3.14 | Provision of extra car parking spaces | 12000000 | 2024-04-01 | 12000000 |  |  | ESO/HRA | Extra parking spaces | Demarcated parking lots | Safe parking lots
|  | 3.15 | Purchase and furnishing of portacabin for office use | 8500000 | 2024-02-01 | 8500000 |  |  | ESO/HRA | Furnished portacabin | Parttioned portacabin | Office accomodation for service support staff
|  | 3.16 | Maintenance of generator | 12000000 | Jan-Dec 24 | 12000000 |  |  | ESO/HRA | Generator | RegularPower supplies | Alternate Power supplies
|  | 3.17 | Purchase of diesel | 10000000 | Jan-Dec 24 | 10000000 |  |  | ESO/HRA | Diesel | Power supplies | Power supplies
|  | 3.18 | Fumigation of the Secretariat premises | 3000000 | Jan-Dec 24 | 3000000 |  |  | ESO/HRA
|  | 3.19 | Cleaning |  | Jan-Dec 24 |  |  |  | ESO/HRA
|  | 3.2 | Servicing of fire Extingushers | 3600000 | Jan-Dec 24 | 3600000 |  |  | ESO/HRA | Extinguisher devices | Safe environment | Fire safety devices
|  | 3.21 | Occupational Safety training | 7500000 | Jan-Dec 24 | 7500000 |  |  | ESO/HRA | Training held | Safety Conscious Staff | Attendance/Report
|  | 3.22 | Sinking of Borehole | 4500000 | 2023-03-01 | 4500000 |  |  | ESO/HRA | Borehole | Alternate Water supply | Constant water supply
|  | 3.23 | Purchase of multi-purpose German working tool box | 3500000 | Jan-Dec 24 | 3500000 |  |  | ESO/HRA | Toolbox | Availability of tools to fix Faults | Availability of working tools
|  | 3.24 | Modification of security posts | 6500000 | Jan-Dec 24 | 6500000 |  |  | ESO/HRA | Security Posts
|  | 3.25 | Conduct training, staff promotion, staff travels and staff retreat.-Occupational Safety training | 257574518 | Jan-Dec 24 | 257574518 |  |  | HRA | Report of activities | Improved staff capacity, knowledge and understanding to deliver on the NEITI mandate | Increase in staff performance and productivity
|  | 3.26 | Coordinate staff welfare and health services | 95843782 | Jan-Dec 24 | 95843782 |  |  | HRA | Contract with service providers | Motivated and healthy workforce. | Improved healthcare for Staff Motivated staff
|  | 3.27 | Maintenance of office complex and operational equipment - Mainetenace of motor vehicles/transport equipment - Maintenance of office furniture - Maintenance of office building - Maintenance of Plants/Generators - Other Maintenance services -Maintenance of Electricals,Air- Conditioners,Plumbing,Water Dispensers facilities -Maintenance of Elevator -Re-painting of the Offices -Re-piping of ES, CD(ESO), Finance, EMRD toilet wings. -Servicing of fire Extingushers | 98447661 | Jan-Dec 24 | 98447661 |  |  | HRA | Contract with service providers | Enhanced operational and administrative excellence | Improved Operational and administrative excellence
|  | 3.28 | Payment of utilities servicies - Electricity charges - Telephone charges - Internet access charges - Water rates - Sewerage charges | 34619205 | Jan-Dec 24 | 34619205 |  |  | HRA | Receipts of payment for services provided | Improved,serviced, and utilized working environment. | Improved,serviced, and utilized working environment
|  | 3.29 | Secured and Insured operational tools, assets and workforce | 62047979 | Jan-Dec 24 | 62047979 |  |  | HRA | Contract with service providers | Secured and Insured operation tool,asset and workforce | Secured and Insured operation tool,asset and workforce
|  | 3.3 | General Administration support and Management -Review of HR Manual -Setting-up and administration of zonal offices -Security services -Purchase of office stationaries -Protocol services, travel and transport logistics -Purchase of drugs and medical supplies -Office Rent -Cleaning and fumigation -Operational vehicles and generator fuel cost - Refreshment and Meals -Postages and Courier Services -Sporting Activities -Purchase of motor vehicles -Purchase of office furniture and fittings -Purchase of alternative power generating set -Purchase of higher capacity generator -Purchase of energy saving security lights -Provision of extra car parking spaces -Purchase and furnishing of portacabin for office use -Purchase of diesel -Fumigation of the Secretariat premises -Sinking of Borehole | 657493380 | Jan-Dec 24 | 657493380 |  |  | HRA |  | Enhanced operational and administrative excellence | Improved Operational and administrative excellence. ( Reviewed HR Manual, New Zonal offices Secured, provision of stationaries/consumables, office security provided).
|  | 3.31 | Develop 2024 Audit Prgram/Plans | - | Jan 24 | - |  |  | Internal Audit | 2024 Audit Plan | Improve Efficiency in the management of resources and operations | Internal Audit Report to mangement and NSWG
|  | 3.32 | Develop Audit Standard Operating Procedure | - | Jan 24 | - |  |  | Internal Audit | Audit operating manual
|  | 3.33 | Conduct Financial Management Risk Assessment | 2500000 | Jan-Dec 24 | 2500000 |  |  | Internal Audit | Risk profile |  | Improve Efficiency in the management of resources and operations
|  | 3.34 | Conduct compliance assessment of operational, financial & IT policies and procedures set by NSWG & management & Evaluate internal control mechanisms to safeguard assets and improve operations | 8878777 | Jan-Dec 24 | 8878777 |  |  | Internal Audit | Compliance assessment report | Implementation of value driven policies, procedure and processes for optmised resource application and management | Improve Efficiency in the management of resources and operations
|  | 3.35 | Meetings/engagement with the Office of Auditor General of the Federation, Accountant General of the Federation and the SGF office | 10000000 | Jan-Dec 24 | 10000000 |  |  | Internal Audit | Report of meetings and engagement |  | Improve Efficiency in the management of resources and operations
|  | 3.36 | Legal Services (Retainership and Consultancy Services) | 21000000 | Jan-Dec 24 | 21000000 |  |  | LEGAL | Contract from service provider | Signed contracts, Reports | Appropriate Legal Representation
|  | 3.37 | Procure law books and other legal materials | 2000000 | Jan-Dec 24 | 2000000 |  |  | LEGAL | Procured law books and legal items |  | Fully resourced Legal Unit
|  | 3.38 | Manage and coordinate NSWG meetings and other NSWG activities | 81406643 | Jan-Dec 24 | 81406643 |  |  | LEGAL | Report of the meetings and activities | Compliance with EITI Requirements, Full participation of Government,Companies, and civil society in the EITI Process, Prepared Memos and Approved Memos, Full compliance with EITI Standard | Paid NSWG sitting, Activity Plan, Number of meetings(4), Minutes of meetings Board resolutions/approvals
|  | 3.39 | Acquire and deploy tracking devices to track public use of NEITI data and visits to the NEITI website | 1000000 | JAN-DEC | 1000000 |  |  | COMMS | Tracking device deployed | Well informed Stakeholders with adequate knowledge of the extractive sector | Number of visits to the website and followership on NEITI Official platforms.
|  | 3.4 | Subscribe to modern apps to support the development of creative designs of infographics and videography for NEITI. |  | JAN-DEC |  | DONOR |  | COMMS | Infograpgics and videography software and apps | Increase understanding of the Extractive Sector | Number of applications used and number of post and followers on social media
|  | 3.41 | Valuation of the NEITI permanent office building | 7000000 | Q1-Q4 | 7000000 |  |  | FINANCE/ACC | Valuation report | A report showing the fair market value of the NEITI building | Fair market value of the NEITI building
|  | 3.42 | Update Fixed Asset Register | 7500000 | Q1-Q4 | 7500000 |  |  | FINANCE/ACC | Report | Fixed Asset Register | Improved F/A Register
|  | 3.43 | Digitize and secure NEITI financial records | 4000000 | Q1-Q4 | 4000000 |  |  | FINANCE/ACC | Digitized Financial Records | A fully digitized Financial documents database | Digitized Financial documents database
|  | 3.44 | Implement the upgraded Integrated Personnel Payroll Information System (IPPIS) | 4000000 | Q1-Q4 | 4000000 |  |  | FINANCE/ACC | Upgraded IPPIS Platform | Upgraded IPPIS system | Timely Salary Payment
|  | 3.45 | Implement the Government Information Financial Information System (GIFMIS) - Cash Management Module | 3000000 | Q1-Q4 | 3000000 |  |  | FINANCE/ACC | GIFMIS Cash Management Module | Upgraded GIFMIS System | Improved GIFMIS Platform
|  | 3.46 | Implement the New Accounting enterprise resource software to include GAAP, IPSAS, and donor reporting | 30000000 | Q1-Q4 | 30000000 |  |  | FINANCE/ACC | A New Accounting enterprise resource software to include GAAP, IPSAS, and donor reporting | ERP software Acquired | ERP Deployed
|  | 3.47 | Train and certify finance and account staff | 2750000 | Q1-Q4 | 2750000 |  |  | FINANCE/ACC | Training report and certificates | Trained ERP staff | Certified ERP staff
|  | 3.48 | Upgrade accounting software | 9000000 | Q1-Q4 | 9000000 |  |  | FINANCE/ACC | Contract from service provider | Reliable and Timely Accounting records | True and Reliable Financial reports
|  | 3.49 | Meetings and engagement with HOR, SENATE, MOF, MOB&NP, FIRS, FCT Inland Revenue Service, etc. | 8500000 | Q1-Q4 | 8500000 |  |  | FINANCE/ACC | Report of the meeting and attendance list | Better relationship with key financial stakeholders | Better relationship with key financial stakeholders
|  | 3.5 | Engage external auditors for statutory audit of NEITI Account | 8000000 | Q1-Q4 | 8000000 |  |  | FINANCE/ACC | Contract with the external auditor and the audit report | Full Compliance to Internal & External Accounting control System | Full Compliance to Internal & External Accounting control System
|  | 3.51 | Conduct annual capacity building for staff on FOI and respond to all Freedom of Information requests. | 600000 | Jan-Dec 24 | 600000 |  |  | COMMS/HR | Participants lists, report | Available and accessible quality Extractive Industries Information and data | Number of FOI request received and responded to.
|  | 3.52 | Review of NEITI Act. | 20000000 | Jan-Dec 24 | 20000000 |  |  | LEGAL | Proposal for revised act | Proposed Amendment | Bill for amendment
|  | 3.53 | Purchase of ICT Hardware | 15000000 | Jan-Dec 24 | 15000000 |  |  | ICT | Contract and receipts from service provider | ICT Hardware Acquired | Improved General Administration Function
|  | 3.54 | Purchase of ICT Software | 12000000 | Jan-Dec 24 | 12000000 |  |  | ICT | Contract and receipts from service provider | ICT Software Acquired | Improved General Administration Function
|  | 3.55 | Upgrade/renewal of Internet Bandwidth | 19000008 | Jan-Dec 24 | 19000008 |  |  | ICT | Contract and receipts from service provider | Reliable, Timely and Speedy Internet Access | Improved General Administration Function
|  | 3.56 | NEITI Website Management and Content | 5000000 | Jan-Dec 24 | 5000000 |  |  | ICT |  |  | Improved General Administration Function
|  | 3.57 | Consultancy services | 7000000 | Jan-Dec 24 | 7000000 |  |  | ICT |  |  | Improved General Administration Function
|  | 3.58 | ICT Data Centre | 120000000 | Jan-Dec 24 | 120000000 |  |  | ICT |  |  | Improved and conducive working environment
|  | 3.59 | Subscriptions, Consumables & Others | 38000004 | Jan-Dec 24 | 38000004 |  |  | ICT |  |  | Improved Consumable Support
|  | 3.6 | NAMS upgrade & Capacity Building | 32000000 | Jan-Dec 24 | 32000000 |  |  | ICT |  |  | Installed NAMS
| Objective 3 Total |  |  | 1875361957 |  | 1855361957 | 35000000 | -15000000
| OVERALL TOTAL |  |  | 2825461957 |  | 2487461957 | 338000000 | -15000000

## Sheet2
#REF!