## Sheet1
DRAFT NIGERIA EITI 2025 COUNTRY WORK PLAN FINANCIALS
NIGERIA EITI 2026 COUNTRY WORK PLAN - FINANCIALS
FUNDING SOURCES
Strategic Objectives | Activity Nunber | Budget Line Items/Activities | Total Cost (Naira) | Timeline | FGN | Donor | Short Fall/Funding Gap | Responsible Department | Output/Outcome
OBJECTIVE 1: Strengthen extractive sector governance and reforms through policy research, strategic stakeholder engagement, communication, and inter-agency collaboration | 1 | Research, Studies on Extractive Industry & Anti-corruption
| 1.01 | Study on the Impact of Energy Transition on Nigeria's Economy, including engagment with oil companies, valdation and launch of the report | 191000000 | June |  | 191000000 |  | PPS | Reports of the study
| 1.02 | Quarterly FAAC Review, and Knowledge Sharing Sessions |  | Jan-Dec |  |  |  | PPS | FAAC Report, Attendance and Reports
| 1.03 | Study on drivers of Illicit Financial Flows in Mining Sector. |  | Mar |  |  |  | PPS | Report of the study
| 1.04 | Assessment of management of Funds set up by PIA 2021 | 73668000 | April | 73668000 |  |  | PPS | Report of the study
| 1.05 | Assessment of Minerals & Mining Act 2007, Mining Roadmap 2016. | 73668000 | May | 73668000 |  |  | PPS/E&M | Report of the study
| 1.06 | Study on PMS Cost - Assessment of under-recovery on PMS Consumption & NNPCL Remittances to the Federation Account | 136860850 | Mar-Dec | 136860850 |  |  | PPS/E&M | Report of the study
| 1.07 | Development of NEITI Gender policy |  | Apr-Jul |  |  |  | PPS | Gender Policy
| 1.08 | Research Studies on Anti-corruption and Governance Initiatives | 94478895.7 | Jan-Dec | 94478895.7 |  |  | TUGAR | Research Paper
| 1.09 | Corruption Risk Assessment in the Nigerian Ports – Implementation of the Integrity Plan |  | Jan-Dec |  |  |  | TUGAR | Report of findings
| 1.1 | Review of Nigeria’s Implementation of the UNCAC – implementation of the Remediation Plan. |  | Jan-Dec |  |  |  | TUGAR | Report
| 1.11 | Follow up activities on TI-CPI analysis and the implementation of Executive Order 1 |  | Jan-Dec |  |  |  | TUGAR | Report
| 1.13 | Follow up activities on TUGAR Ethics Survey and Gap Analysis. |  | Jan-Dec |  |  |  | TUGAR | Report
| 1.14 | Implementation of the National Anti-corruption Strategy (NACS) 2022 - 2026 |  | Jan-Dec |  |  |  | TUGAR | Report of meetings
| 1.15 | Coordination of Anti-corruption agencies on the platform of the IATT |  | Jan=Dec |  |  |  | TUGAR | Report of meetings
| 1.16 | Joint Commemoration of the International, and Africa Anti-corruption Days 2026 |  | Mar-Dec |  |  |  | TUGAR | Report and Action Plan
|  |  | 569675745.7 |  | 378675745.7
| 2 | Capacity Development on Natural Resource Governance
| 2.01 | Capacity Building Programs on Natural resource governance for NEITI stakeholders- companies, government and civil society | 105000000 | Jan-Dec | 105000000 |  |  | Communication | Report and participant list
| 2.02 | Capacity building programs for committee of the National Assembly on EITI/NEITI process | 45069491.83 | Jan-Dec | 45069491.83 |  |  | Communication | Report and participant list
| 2.03 | Stakeholders engagements on 2026 EITI Validation exercise activities | 57734920 | Apr-Dec | 57734920 |  |  | Validation Committee | Report & participant list
| 2.04 | Capacity building for staff on research, development of policy briefs & advisories | 10000000 | March | 10000000 |  |  | HRA/PPS | Participant list and trainign report
| 2.05 | Conduct stakeholders engagement on Gender inclusion and Mainstreaming in Extractive Industries activities. | 10000000 | Aug - Sept | 10000000 |  |  | Communications/PPS | Report & participant list
| 2.06 | Roundtable meetings with Anti-Corruption Agencies on compliance and enforcement of recommendations from NEITI Audit Report | 5000000 | Jan-Dec | 5000000 |  |  | Legal | Report and participant list
|  |  | 232804411.83 |  | 232804411.83
| 3 | Communications, Stakeholders Engagements & Outreach Activities on EITI/NEITI
| 3.02 | NEITI Quarterly House Dialogue Series-Topical issues on Natural Resource governance |  | Jan-Dec |  |  | 20000000 | Communication | Report & participant list
| 3.03 | Public presentation of NEITI oil, gas, mining and FASD reports |  | Jan-Dec |  |  | 20000000 | Communication/E&M | Report & participant list
| 3.04 | Collaborations and strategic partnerships eg. NESG, Nigerian Mining Week, NAEC, Mining Indaba |  | Jan-Dec |  |  |  | Communication | Report & participant list
| 3.05 | Zonal outreaches at geo-politcal zones - roadshows & town-hall meetings at sub-national level. | 40000000 | Jan-Dec | 40000000 |  |  | Communication | Report & participant list
| 3.06 | Press briefings on NEITI activities and industry trends. | 16000000 | Jan-Dec | 16000000 |  |  | Communication | Media report
| 3.07 | Public enlightenment programs using traditional media, features and Op-ed: Jingles, commercials and social media campaign etc. | 21000000 | Jan-Dec | 21000000 |  |  | Communication | Media report
| 3.08 | Youth-targeted sub-national advocacy & engagements |  | Jan-Dec |  |  | 20000000 | Communication | Report & participant list
| 3.09 | Printing and publication NEITI 2024 oil, gas, mining & FASD reports, policy papers and knowledge products |  | Jan-Dec |  |  | 20000000 | Communication | Publications
| 3.1 | Produce and print IEC materials for NEITI public and stakehoders engagements, outraech programms and events | 20000000 | Jan-Dec | 20000000 |  |  | Communication | Printed IEC materials
| 3.11 | NEITI media appearances and public engagements on extractive industries issues |  | Jan-Dec |  |  |  | Communication | Media reports
| 3.13 | Simplification of NEITI 2024 Oil &Gas, Mining and FASD reports using videography, animations, cartoons and infographics in local languages and pidgin. | 8766506 | Jul | 8766506 |  |  | Communication | Simplifed copies
| 3.14 | Produce and publish NEITI Newsletter/Magazine | 10000000 | Jan=Dec | 10000000 |  |  | Communication | Copies of newsletters
|  |  | 115766506 |  | 115766506
|  | Sub-Total | 918246663.53 |  | 727246663.53 | 191000000 | 80000000
Objective 2: Sustaiin Extractive reporting & Relevance by focusing on national & interntational priorities | 4 | Oil, Gas, Mining Sectors & Resource Disbursment Audits
| 4.01 | Conduct 2024 Oil and Gas Industry Audit | 136954168.96 | Feb-Oct | 136954168.96 |  |  | E&M | Oil & gas report
| 4.02 | Conduct 2024 Solid Minerals Industry Audit | 89190860.5 | Feb-Oct | 89190860.5 |  |  | E&M | SM report
| 4.03 | Conduct 2024 Fiscal Allocation and Statutory Disbursement Audit | 84393059.8 | Jan-Dec | 84393059.8 |  |  | E&M | FASD report
|  | Sub-total | 310538089.26 |  | 310538089.26
OBJECTIVE 3:Achieve operational excellence in implementing NEITI mandate through Professionalism, innovation, use of technology, resource management, and capacity building. | 5 | NWSG Matters, Secretariat Administration, Staff Trainings/Welfare & Legal Matters
| 5.01 | Retreat for the NSWG, and statutory meetings | 208265979.1 | Jan-Dec | 208265979.1 |  |  | Legal/ES Office | Minutes of meetings
| 5.02 | Design and Acquisition of Software for Extractive Industry Data Centre | 117376191.8 | Jan-Dec | 117376191.8 |  |  | ES office | Functional Data centre
| 5.03 | Impact assessment on EITI implementation in Nigeria. | 35000000 | Mar | 35000000 |  |  | PPS | Assessment report
| 5.04 | Produce 2025 EITI Annual Progers Report, Monitoring & Evaluation Report, and 2027 Country Work Plan, including consultation with stakeholders. | 10000000 | Jan-Dec | 10000000 |  |  | PPS | Reports & work plan
| 5.05 | Develop M&E Framework for 2022-2026 NEITI Strategic Plan, Review the implementation of the Plan, and Develop successor Strategic Plan | 33900000 | Jan-Jun | 39000000 |  |  | PPS | M&E Framework, Report & strategic plan
| 5.07 | Review of Nigeria's implementation of 2023 EITI Standard, Corrective Actions from last Validation, and Coordinate the next Validation Exercise | 10000000 | Jan - Jul | 10000000 |  |  | PPS/Validation Committee | Report & Succesful EITI Validation exercise
| 5.08 | Update and manage contents on the NEITI website, identify and deploy suitable tracking devices to track public use of NEITI data and visits to the website and all social media platforms. |  | Jun |  |  | 10000000 | Communication/ES Office | Efficient website
| 5.09 | Electronic Document Management System (EDMS) with Workflow for internal operations an records keeping. |  |  |  |  | 65000000 | ES office | EMS installed
| 5.1 | Upgrade of ICT Eqipments & Sofrtware - Optimization of Systems, Storage, Software and Network Security. | 67200000 | Jul | 67200000 |  |  | ES office | Efficient storage, network security system
| 5.11 | Review of NEITI Act & Legal Services | 22500000 | Jan-Dec | 22500000 |  |  | Legal/ES Office | Revised NEITI Act
| 5.12 | Subscribe to modern apps to support the development of creative designs of infographics and videography for NEITI |  | Jun |  |  | 5000000 | Communication/ES Office | Creative designs of infographic and videographic fof NEITI
| 5.13 | Procure books, legal materials, newspapers & magazines | 6044601.07 | Jan-Dec | 6044601.07 |  |  | Leagal/HRA | Availability of relevant books and newspapers
| 5.14 | Staff capacity building, training & travels, wefare, sport, and insurance premium | 666160723.23 | Jan-Dec | 666160723.23 |  |  | HRA | Training reports & improved staff welfare
| 5.15 | General Admistration, Maintanance, Utilities & Purchase of library books, equipments, photocopiers, computers, furtntures, vehicles, generator. | 1044494118.85 | Jan-Dec | 1044494118.85 |  |  | HRA | Smooth & efficient adminstration
| 5.16 | NEITI House & Premise Improvement | 122888874.5 | Jan-Dec | 122888874.5 |  |  | HRA | Facelift of NEITI Secretariat
| 5.17 | Financial consulting - digitalising NEITI financial records, upgrade of accounting software, update of organization risk profile, and engagement of external auditors for NEITI Operations | 183481156.5 | Jan-Dec | 183481156.5 |  |  | F&A/ES Office | Digitised and error proof financial records, upgraded financial & accounting platforms
|  | Sub-total | 2527311645.05 |  | 2532411645.05 |  | 80000000
|  | GRAND TOTAL | 3756096397.84 |  | 3570196397.84 | 191000000 | 160000000

## Sheet2
63515000
210480000 | 13470000
134969851 | 13470000 | 62880000
195515500 | 13470000 | 15720000
| 103925000 |  | General Secretariat administration and operations. These include: Operational expenses; Office stationeries, Working tools and equipment, subscriptions to research applications and creative designs, fuel, internet subscriptions, transport logistics, alternative power supply to thesecretariat-Solar, Generator maintenance, purchase of magazines, printing of non-security documents etc
540965351