## Sheet1
DRAFT NIGERIA EITI 2025 COUNTRY WORK PLAN FINANCIALS
NIGERIA EITI 2025 COUNTRY WORK PLAN FINANCIALS
FUNDING
Strategic Objectives | Activity Nunber | Budget Line Items/Activities | Total Cost (Naira) | Timeline | FGN | Donor | Short Fall / Funding Gap | Responsible Organization/Department | Output | Expected Outcome | Outcome Indicator
OBJECTIVE 1: Strengthen extractive sector governance and reforms through policy research, strategic stakeholder engagement, communication, and inter-agency collaboration | 1 | Research, Studies on Extractive Governance & Anti-Corruption
| 1.01 | Study on Rethinking state participation in the mining sector: Effective models for the (proposed) Nigeria Solid Minerals Development Company. | 4500000 | March | 4500000 |  |  | PPS | Reports of Findings and Recommendation | Policy Engagement with MSMD on findings and recommendations | Media reports of Policy Engagement
| 1.02 | Study on Evaluating the revenue effect of the Gas Commercialisation Policy in gas production and utilization. | 4500000 | October | 4500000 |  |  | PPS | Reports of Findings and Recommendation | Policy Engagement with MPR, NUPRC and Gas stakeholders | Media reports of Policy Engagement
| 1.03 | Study on The urgent need to activate non-performing PSCs to maximise revenue contribution from Nigeria’s oil and gas resources. | 37940000 | June | 4500000 |  |  | PPS | Reports of Findings and Recommendation | Policy Engagement on reasons for non performing PSCs | Reports of Policy Engagement
| 1.04 | Study on Optimising oil and gas revenue collection through effective enforcement of remittances by covered entities. | 3000000 | January | 3000000 |  |  | PPS | Reports of Findings and Recommendation | Improved revenue collection from covered entities | Declining figure of outstanding collectible revenues in NEITI Audit report
| 1.05 | Study on control of emissions in the oil and gas sector | 62880000 | October |  |  | 62880000 | PPS | Policy Advisories | Policy Engagement with MPR, NUPRC and Gas stakeholdersCommitment to the revision of the GCP by the sector regulators | Reports of Policy Engagement
| 1.06 | Study on state of the refineries and impact on the Nigerian economy | 52000000 | April | 52000000 |  |  | PPS
| 1.07 | Study on the Impact of Energy Transition on Nigeria's Economy | 132000000 | June |  | 132000000 |  | PPS | Reports of study on Energy Transition Economic Impact | To determine and Establish the scope and sector of impact of the transition
| 1.08 | Consultation with relevant government and industry actors and other non-state actors on Energy transition | 170000000 | Jan-Sept |  | 170000000 |  | PPS | Attendance and Reports | Findings and Recommendations of the study | Findings and Recommendations in the final report
| 1.09 | Conduct at least 4 policy dialogues on extractive industry studies | 48000000 | Jan-Dec | 48000000 |  |  | PPS
| 1.1 | Produce 4 (four) Quarterly Review of FAAC and conduct 1 (one) knowledge sharing session on FAAC analysis | 14000000 | Jan-Dec | 12000000 |  |  | PPS | FAAC Report, Attendance and Reports | Stakeholder Engagements and public debate on Federation Account revenue and disbursements, Improved Understanding of FAAC Data by NEITI staffs and stakeholders | News report, media mentions, literature reference of NEITI Quarterly Review and Expanded scope of NEITI Quarterly FAAC report
| 1.11 | Study on PMS consumption in Nigeria | 28500000 | Mar-Dec | 28500000 |  |  | PPS | Participant list and trainign report | Improved capacity of staffs on research and study | Better quality research output
| 1.12 | Development of NEITI Gender policy | 20000000 | Apr-Jul | 20000000 |  |  | PPS | PPS/ENERGY &MINESING
| 1.13 | Research Studies on Anti-corruption and Governance Initiatives | 40000000 | Q1 - Q4 | 40000000 |  |  | TUGAR | Validation Meeting Report Report of Survey Launch of Report | Data available for better coordination and implementation of anti-corruption and governance initiatives | Consultant Procured Updated Report Report Launched and diseminated
| 1.14 | Follow up activities on the TI-CPI analysis and the implementation of Executive Order 1 | 15000000 | Q1 - Q4 | 15000000 |  |  | TUGAR | Report of findings and recommendations | better undertatnding of the ranking for better understanding and engagement for improved ratings | clearly stated steps and recommendations on how to improve Nigeria's ranking in the TI-CPI
| 1.15 | Corruption Risk Assesment - Ports Sector | 15000000 | Q1 - Q4 | 15000000 |  |  | TUGAR | Report Launch of Report | Reduction of corruption and improved transparency in the sector | reporting and achievements in the sector supported by empirical data Report Launched and diseminated
| 1.16 | Implementation of findings of Scoping Survey and Gap Analysis of the Ethics Framework in Nigeria - follow up actvities | 15000000 | Q1 - Q4 | 15000000 |  |  | TUGAR | Report of Trainings | Better understanding and implementation of of the Codes of Conduct for Public Officers as a preventive tool in the fight against corruption | No. of public officers trained using the virtual training portal developed by TUGAR
| 1.17 | Implementation of the National Anti-corruption Strategy (NACS) 2022 - 2026 | 5000000 | Q1 - Q4 | 5000000 |  |  | TUGAR | Report of meetings Data collection Template | Better implementation of the NACS | Availability of data on implementation of the NACS
| 1.18 | Inter Agency Cooperation and collaboration - Coordination of Anti-corruption agencies on the platform of the IATT | 10969851 | Q1 - Q4 | 10969851 |  |  | TUGAR | Report of meetings | Greater interagency cooperation and collaboration | Report of events
| 1.19 | Review of Nigeria's implementation of the UNCAC Meetings - Intergovernmental Sessions of the Implementation Review Group (IRG) Conference of States Parties to the United Nations Convention Against Corruption 2025 Resolution Drafting and post resolution Meetings | 30000000 | Q1 - Q4 | 30000000 |  |  | TUGAR | Reports, Country Statements Statements | Greater cooperation and synergy amongst ACAs in meeting Nigeria's treaty obligations under the UNCAC | Report and Country statements at IRG, CoSP and other meetings
| 1.2 | Joint Commemoration of the International Anti-corruption Day 2025 | 2000000 | Q4 | 2000000 |  |  | TUGAR | Report and Action Plan | Improved Synergy and inter agency cooperation and collaboration | Greater synergy among anti-corruption initiatives
| 1.21 | Joint Commemoration of the African Anti-corruption Day | 2000000 | Q2 | 2000000 |  |  | TUGAR | Report and Action plan |  | Greater synergy among anti-corruption initiatives
|  | Sub-Total | 712289851 |  | 311969851 | 302000000 | 62880000
| 2 | Capacity Building on Natural Resource Governance
| 2.01 | Organise natural resource governance programmes/activities for NEITI stakeholders- companies, government and civil society on extractive issues. | 70000000 | Jan-Dec | 70000000 |  |  | COMMS |  | Improved Relevance and impact of NEITI in natural resource issues, in which NEITI should collaborate, participate and organize, schedule and give wide publicity.
| 2.02 | Exposure of the relevant committees of the National Assembly on the 2023 EITI Standard and legislative engagement of NEITI's reports | 61000000 | Jan-Dec | 61000000 |  |  | COMMS |  | Same Above Increased state and non-state actors’ advocacy and public participation in the EITI implementation process | Number of Meetings Held and Appearances at NASS
| 2.03 | Quarterly NEITI House Dialogue Series-Topical issues on Natural Resource governance | 20000000 | Jan-Dec | 20000000 |  |  | COMMS |  | Well informed Stakeholders with adequate knowledge of the ongoing reforms in the extractive sector | Number of Dialogue held
| 2.04 | Prepare stakeholders for Nigeria's validation by the EITI (Conduct series of capacity building initiatives-Townhall meetings, Dialogues, Focus Group Discussions, etc for both NEITI internal and external publics) | 55000000 | Apr-Dec | 55000000 |  |  | COMMS
| 2.05 | Conduct engagements with relevant government agencies & Extractive Companies on climate change and control of emmissions | 10000000 | April | 10000000 |  |  | COMMS/PPS
| 2.1 | Conduct engagement with stakeholders on climate change and control of emmissions (CSO, media , staff etc) | 15000000 | Jun-Jul | 15000000 |  |  | COMMS/PPS |  | Broadened stakeholders Knowledge and understanding on Energy transition. | Participants list. Media mention and programme report.
| 2.11 | Capacity building for staff on research, development of policy briefs & advisories | 15000000 | March | 15000000 |  |  | PPS/HR&ADM | Participant list and trainign report | Improved capacity of staffs on research and studies | Better quality research output
| 2.12 | Organize stakeholders engagement on Gender inclusion and Mainstreaming in Extractive Industries activities. | 10000000 | Aug - Sept | 10000000 |  |  | COMMS/PPS |  | Improveed stakeholders understanding on the importance of gender equity and inclusion in the extractive sector operations. | Media reports, -Release of the report. -Participants list -Programme report.
| 2.13 | Organise public lecture on International Women’s Day | 7000000 | Jan-Mar | 7000000 |  |  | COMMS/PPS |  | Increased women participation in the extractive sector. Improved public understanding on gender equity and inclusion the extractive industries. | Media reports. Release of the report. Participants list Programme report.
| 2.14 | Conduct Round table with relevant Government Agencies on Environmental Sustainability/ climate change | 7000000 | Oct-Nov | 7000000 |  |  | COMMS/PPS | Draft Reports | Policy measures on mitigating climate change, global warming. Increased knowledge on climate change and global -warming issues. Sustained public campaign and awareness against climate change and global warming. | Media Mentions Participants list Programme report.
| 2.15 | Conduct roundtable meetings with Anti-Corruption Agencies on compliance and enforcement of recommendations from NEITI Audit Report | 5000000 | Q1-Q4 | 5000000 |  |  | LEGAL | Minutes of Meetings | Improved synergy with ACAs on implementation of NEITI Audit Recommendations and findings | No of issues resolved, cases and investigations initiated/resolved by ACAs
|  | Sub-Total | 275000000 | 0 | 275000000 | 0 | 0
| 3 | Communications, Stakeholders Engagements & Outreach Activities on EITI/NEITI
| 3.01 | Policy engagements on the three proposed Bills in the solid minerals sector | 15720000 | Jan-Dec |  |  | 15720000 | ENERGY & MINING/PPS/COMMS |  | NEITI position and policy engagements on the Tax Reform Bill, NEITI position and policy engagement on the proposed Bills for the reform of the solid minerals sector
| 3.02 | Policy dialogue on Tax Reform Bills | 10000000 | March |  |  | 10000000 | COMMS
| 3.03 | Develop framework for stakeholders engagements-Companies, Government, Civil Society, sub-nationals, including the review of the stakeholders map etc | 20000000 | Jan-Mar |  |  | 20000000 | COMMS |  | Stakeholders with adequate knowledge of NEITI/ EITI Process. Revised stakeholder map | Framework for engaging with different stakeholders developed. Stakeholders Map developed
| 3.04 | Conduct stakeholders engagements/public enlightenment program on NEITI reports and knowledge products- Roadshows, Townhall Meetings, outreaches etc at the Sub-national level (6 geo-political zones), Identifying and engaging policy champions at all levels of government on NEITI/EITI issues. | 35000000 | Jan-Dec | 35000000 |  |  | COMMS |  | Exposure of the information and data contained in the NEITI Industry Reports to Stakeholders as enshrined in the NEITI Act 2007 | Attenandance and Mediua Media Mentions
| 3.05 | Presentation of NEITI industry reports of the oil, gas, mining and FASD | 20000000 | Jan-Dec |  | 20000000 |  | COMMS |  | Exposure of the information and data contained in the NEITI Industry Reports to Stakeholders as enshrined in the NEITI Act 2007 | Stakeholders with adequate knowledge of global trends in the extractive sector. Number of public presentations held and attendance at the presentations.
| 3.06 | Identify programs by strategic organizations for collaborations and strategic partnerships eg. NESG, Nigerian Mining Week, NAEC, Mining Indaba | 5000000 | Jan-Dec | 5000000 |  |  | COMMS |  | Strategic partnerships/ collaborations built with credible and reputable Association for increased visibility and relevance of NEITI | Report of collaborative programs
| 3.07 | Media relations and activities to educate and inform stakeholders and the public about the NEITI process and extractive industry issues through traditional media programmes such as editorials, features and Op-ed, including quarterly press briefings | 15000000 | Jan-Dec | 15000000 |  |  | COMMS | Media mentions of NEITI; Appearances of relevant stakeholders on EITI/NEITI in the media and public discuss | improved visibility, relavance and Impact of NEITI in natural resource governance discuss. |  Increased public enlightenment of the EITI process and emerging global trends and enhance impact and relevance in Nigeria Extractive sector.  No of media appearances and mentions
| 3.08 | Simplification of NEITI 2022, 2023 and 2024 Oil &Gas, Mining and FASD reports using videographs, animations, cartoons and infographics in English, local languages and pidgin. | 15000000 | Jan-Dec | 15000000 |  |  | COMMS | Simplified copies of the NEITI industry reports and some knowledge products | To communicate, inform, equip and empower the citizens with information and data on Nigeria and global extractive industries issues to demand accountability on revenue generation and utilization. | Well-informed and equipped citizens with knowledge of extractive sector revenue generation and utilization demanding accountability.
| 3.09 | Develop and place public information, education and enlightenment messages on the NEITI/EITI Process- Jingles, Commercials and social media campaigns, while identifying new modes, platforms and channels of communication and activate them. | 45000000 | Jan-Dec |  |  | 45000000 | COMMS |  | Underdtanding of NEITI/EITI process and emerging global trends. | Number of IEC Materials produced.
| 3.1 | Upgrade and content management of the NEITI website, identify and deploy suitable tracking devices to track public use of NEITI data and visits to the website and all social media platforms. | 5000000 | Jan-Dec | 5000000 | NIL |  | COMMS |  | Well-informed Stakeholders with adequate knowledge of the extractive sector. | Number of visits to the website and followership on NEITI Official platform.
| 3.11 | Printing of NEITI knowledge products and specific publications targeted at strategic stakeholders for use in the policy dialogues and all engagements on NEITI's programs and activities | 20000000 | Jan-Dec | 20000000 |  |  | COMMS |  | Underdtanding of NEITI/EITI process and emerging global trends. | Number Reports Disseminated
| 3.12 | Quarterly NEITI House Dialogue Series-Topical issues on Natural Resource governance | 20000000 | Jan-Dec | 20000000 |  |  | COMMS |  | Well informed Stakeholders with adequate knowledge of the ongoing reforms in the extractive sector | Number of Dialogue held
| 3.13 | Capacity building for stakeholders on the 2023 EITI Standard and expectations from Nigeria | 30000000 | Apr-Dec |  | 30000000 |  | COMMS
| 3.14 | Capacity building for multi-stakeholders on emerging issues in natural resource governance - (civil society, media, government agencies and companies on energy transition, gender, anti-ccorruption, climate change and carbon emissions | 40000000 | May |  | 40000000 |  | COMMS |  | Improveed stakeholders understanding on the EITI emerging issues and importance of gender equity and inclusion in the extractive sector operations.
| 3.15 | Specialised trainings, workshops and support to the network of Persons Living With Disabilities to understand and engage in the EITI/NEITI process for inclusivity. | 20000000 | Jan-Dec |  |  | 2000000 | COMMS | Minutes of Meetings, Reports. | Increased participation and understanding of Persons Living With Disabilities of the EITI process | Media Mentions, Participants list and Programme report.
|  | Sub-Total | 315720000 | 0 | 115000000 | 90000000 | 92720000
| 4 | Conduct and Publish 2024 Oil and Gas Industry Audit | 195648812.8 | Feb-Sep | 195648812.8 |  |  | ENERGY & MINING |  |  | Oil and gas sector report
| 4.01 | Conduct and Publish 2024 Solid Minerals Industry Audit | 127415515 | Feb-Oct | 127415515 |  |  | ENERGY & MINING |  |  | Mining sector report
| 4.02 | Conduct and Publish 2024 Fiscal Allocation and Statutory Disbursement Audit | 120561514 | Jan-Dec | 120561514 |  |  | ENERGY & MINING |  |  | FASD report
|  | Sub-total | 443625841.8 | 0 | 443625841.8 | 0
OBJECTIVE 3:Achieve operational excellence in implementing NEITI mandate through Professionalism, innovation, use of technology, resource management, and capacity building. | 5 | Retreat for the NSWG, coordination of statutory meetings, site visits, grassroots mobilisation and other related Activities | 208265979.1 | Q1-Q4 | 208265979.1 |  |  | LEGAL | Report of meetings and activities | Compliance with EITI requirements; full participation of Government, Companies and Civil Society in the EITI Process prepared | sitting and travel allowances of NSWG paid; activities plan; No. of Meetings (4); Minutes of Meetings, Board resolutions/approvals
| 5.01 | Establishment of Extractive Industry Data Centre | 167680274 | Jan-Dec | 167680274 |  |  | ICT/ES OFFICE | Live and functional NEITI Data centre
| 5.02 | Review of the NEITI Act, engagement of a consultant and stakeholders consultations and engagement on the draft bill. | 32400500 | Mar-Dec | 32400500 |  |  | LEGAL | Proposal for revised Act | A new or amended NEITI Law | Bill for amendment
| 5.03 | Engagement of consultant to conduct impact assessment on EITI implementation in Nigeria.(2004-2025) and consultation with stakeholders. | 33000000 | March | 33000000 |  |  | PPS
| 5.04 | Develop and publish the 2026 Annual country work plan including consultation with stakeholders. | 5000000 | Oct-Dec | 5000000 |  |  | PPS | • Annual Country Work plan. • Populated 2025 work plan templates by stakeholders. • Report of stakeholder engagement including participants list | *Coordinated implementation of EITI in Nigeria *Donor commitments and partnerships in implementation of country workplan activities | MOUs, letters and reports of collaboration and partnership in the implementation of EITI activities.
| 5.05 | Produce the 2024 Annual Progress Report and validate report with stakeholders | 16000000 | Jan-Jun | 16000000 |  |  | PPS
| 5.06 | Conduct regular monitoring of all NEITI programs and activities. | 12000000 | Jan-Dec | 12000000 |  |  | PPS | *Activity monitoring reports. *Participants list *Media list
| 5.07 | Engage consultant to develop and publish the M&E framework for the NEITI 2022-2026 strategic plan | 35000000 | Jan - Jul | 35000000 |  |  | PPS | *The Monitoring & Evaluation (M&E) Framework For the NEITI 2022 – 2026 Strategic Plan. *80 NEITI staff and stakeholders trained to monitor and evaluate EITI implementation in Nigeria. | Clear measurable indicators for accessing the implementation of the strategic plan. The mid-term and final workplan evaluation, annual progress and strategic plan review reports based on the NEITI M&E framework.
| 5.08 | Development of NEITI comprehensive remediation plan and retreat for IMTT members on implementation | 15000000 | Jan-Dec | 15000000 |  |  | PPS
| 5.09 | Conduct a review and validate report with stakeholders on the implementation of corrective actions and recommendations of the 2023 EITI validation report. | 10000000 | Jan-Dec | 10000000 |  |  | PPS
| 9 | Attendance and participation at International meetings, workshops, conferences and engagements | 163703699.11 | Jan-Dec | 163703699.11 |  |  | HR/ADM
| 10 | Conduct capacity building, specialized, professional, Health, Safety and Enviroment (HSE) training for staff | 104500000 | Jan-Dec | 104500000 |  |  | HR/ADM |  | Improved Relevance and impact of NEITI in natural resource issues, in which NEITI should collaborate, participate and organize, schedule and give wide publicity.
| 11 | Financial consulting including digitalising NEITI financial records, upgrade of accounting software and engagement of external auditors for NEITI Operations | 183481156.5 | Jan-Dec | 183481156.5 |  |  | FINANCE/ACC | Digitised and error proof financial records, upgraded financial platforms, new accounting enterprise | Reports, upgraded financial platforms- IPPIS, GIFMIS, etc | Fixed Asset Registers, digitised financial documents, Full Compliance to Internal & External Accounting control System etc
| 12 | General Secretariat administration and operations. These include: Operational expenses; Office stationeries, Working tools and equipment, subscriptions to research applications and creative designs, fuel, internet subscriptions, transport logistics, alternative power supply to thesecretariat-Solar, Generator maintenance, purchase of magazines, printing of non-security documents etc | 2132579466 | Jan-Dec | 2132579466 |  |  | HR/ADM | Procured Software, Site Subscription | Improved data analysis capacity of research staff, Improved report writing, Easy access to data by research staff | Quality of Data and Analysis, Reduced error and plagiarism count in the report, Improved completion time for knowledge product
|  | Sub-Total | 3118611074.71 |  | 3118611074.71 | 0 | 0
| Grand Total |  | 4865246767.51 |  | 4264206767.51 | 392000000 | 155600000

## Sheet2
63515000
210480000 | 13470000
134969851 | 13470000 | 62880000
195515500 | 13470000 | 15720000
103925000
540965351